## Generic Risk
SBGS Generic Risk Register_OBN-OBC-SWTZ
Area Risk Ratings ( Risidual Risk Rating)
Applicable Yes/No | Hazard Category | Hazard Basic Description | Hazard Generic Description | Potential Consequence (Most Likely Outcome's) | Control Measures Prevention & Mitigation | Reputation | Assets / Financial | Environment | People
Yes | ENVIRONMENT | Threats from Invertebrate | Some invertebrate species can be harmful to people, and many of the world's most dangerous parasites are members of the invertebrate family. Some of the more well-known invertebrate parasites include ticks, fleas, and leeches. Some invertebrates, like mosquitoes, can be especially damaging because they can potentially carry diseases. The most common marine invertebrates are sponges, cnidarians, marine worms, lophophorates, molluscs, arthropods, echinoderms and the hemichordates | Injury or occupational illness ranging from FAC and/or MTC/RWC being the most likely realistic outcome | Project awareness via safety meetings and TBM. Good lighting aboard the vessels and onto ROV / Basket / source arrays during recovery. Personnel equipped with proper PPE. Staffs/Contractors with updated vaccinations up to date Anti-venom availability Mosquito control in hotels/use of AC/sprays/Information about malaria available | B2 | B2 | B1 | C3
Yes | ENVIRONMENT | Threats from Vertebrate | There are many thousands of species of vertebrate that have the potential to be harmful to humans, either attacking with tooth and claw or causing harm though poison/venom, common examples encountered by human interaction off/onshore: Dogs, reptiles, cats, fish. | Injury or occupational illness ranging from FAC and/or MTC/RWC being the most likely realistic outcome | Care and attention, onshore and at hotel facility's - Information via TIS. Staffs/Contractors with updated vaccinations up to date Identified hazardous species, awareness campaigns Anti-venom availability if required | B2 | B2 | B1 | C3
Yes | ENVIRONMENT | Infectious disease | Infectious diseases are disorders caused by organisms — such as bacteria, viruses, fungi or parasites. Many organisms live in and on our bodies. They're normally harmless or even helpful, but under certain conditions, some organisms may cause disease. Some infectious diseases can be passed from person to person. | Isolations and/or medical evacuation of infected staff, resulting in financial loss Infected staffs with MTC illness, likelihood of LWDC. | All personnel are carrying up to date UKOOA / NMD medical certificates. Enforce practices that reduce the likelihood of exposure: appropriate procedures for hand washing, sharps disposing, laundry handling & contaminated material cleaning. Provide personal protective equipment such as gloves, gowns, and masks. Disposable gloves available in all first aid kits. | B1 | C3 | B1 | C3
Yes | ENVIRONMENT | Intestinal parasites | Intestinal parasites are parasites that can infect the gastro-intestinal tract of humans and other animals. Means of exposure include: ingestion of undercooked meat, drinking infected water, and skin absorption. | Injury or occupational illness ranging from FAC and/or MTC being the most likely realistic outcome | Ensure all meats are correctly cooked Reporting system to ensure undercooked meats are identified Food handling training for galley team to be held by crew medics Personal hygiene recommended practices known Use only bottled water or water that has been analysed fit to drink | B1 | C2 | B1 | C2
Yes | ENVIRONMENT | Contaminated food and water | Ingestion of contaminated fresh water or food by different microbes or pathogens agents. Vomiting, diarrhoea, stomach cramps, fever, nausea, headache, in rare cases potentially fatal Food not checked by Medic No water testing No Food handler medical examination for cooks and galley team. Poor Selection of contractors (Ship chandler) Improper food handling and hygiene on-board. No respect of Ship Managers' internal procedures , No respect of OGP Waste Management Guidelines, IAGC Marine Geophysical Manual | Occupational illness of multiple persons on board, ranging from FAC to LWDC being the most likely realistic outcome Replacement of catering contractor | Water analyses performed UV filtration installed on the main water systems. Food handler medical examination for cooks and galley team & Food handling training for galley team. Selection of contractors/contractor management. Food handling and hygiene on-board in camps, monitored. Health and hygiene inspections carried out every week by crew by medics. Garbage Management plan in place aboard all vessels involved in the survey | B1 | C3 | B1 | C3
Yes | ENVIRONMENT | Exposure to Air Pollutant (Natural Gas & H2s) | Natural gas is a hydrocarbon gas mixture consisting primarily of methane, but commonly includes varying amounts of other higher alkanes and sometimes a usually lesser percentage of carbon dioxide, nitrogen, and/or hydrogen sulphide. Natural gas is an energy source often used for heating, cooking, and electricity generation. It is also used as fuel for vehicles Hydrogen sulphide (also known as H2S, Sour Gas) is colourless, toxic and flammable gas and is partially responsible for the foul odour of rotten eggs and flatulence. Hydrogen sulphide is both an irritant and an asphyxiate gas and can cause death | Occupational illness of multiple persons on board, ranging from FAC to LWDC being the most likely realistic outcome, Potential of fatality's have been known pending parts per million dosage | Identification of types of gas i.e. Carbon Monoxide, H2s H2s Training, and /or other pending gas Identification Alarm and monitoring systems, vessel and personal, based on the identified gas and risks Awareness controls such as meetings and posters Carbon monoxide detectors in high risk area. | B1 | B3 | B1 | B4
Yes | ENVIRONMENT | Extreme cold weather | Extreme Cold refers to the condition or subjective perception of having low temperature, the absence of heat, extreme cold can cause Hypothermia is life threatening in some instance i.e. long immersion in cold water, but most common scenario are personal working hard (sweating) and then resting in icy conditions (pneumonia). | Staffs with cold and flue symptoms requiring MTC Asset Loss, due to hose breakage etc... | Reduced exposure through shorter shifts Instruction and Information on extreme cold environments Training on identification of cold related injury's including frostbite Physical fitness of staffs exposed Correct clothing PPE for the environment Mechanical systems checked / hoses inspected / Antifreeze utilised | B1 | C3 | B1 | C3
Yes | ENVIRONMENT | Extreme heat weather | High temperature constitutes a real risk to personnel which results in fatigue, dehydration, and eventually failure of thermal regulating mechanism: The faint symptoms come first, followed by cramps then comes the heat exhaustion and eventually the heat stroke (life threatening). Immersion syncope. Food poisoning situation is more likely to occur under warm climates due to quicker food decomposition. | Staffs requiring MTC due to over heating Asset Loss due to over heating | Reduced exposure through shorter shifts / ensure sufficient water consumption Food monitoring place / controlled by caterer Instruction and Information on extreme heat environments Training on identification of heat related disorders Physical fitness of staffs exposed Correct clothing PPE for the environment Mechanical cooling systems checked / Ventilation systems check | B1 | B3 | B1 | C3
Yes | ENVIRONMENT | Cold water | The definition of cold water is variable. The temperature of thermally neutral water, in which heat loss balances heat production i.e., not shivering, is approximately 33-35° C. Hypothermia eventually results from immersion in water below this temperature, significant risk of immersion hypothermia usually begins in water colder than 25° C. Cold water immersion is associated with two significant medical emergencies: near drowning and hypothermia | Staffs with cold and flue symptoms requiring MTC Potential of being enerced in cold water could result in fatality | MOB system in place efficient for cold environment Fall arresters and guard rails in place Hazardous areas with risk of overboard marked and monitored / No lone workers Correct clothing PPE for the environment | B1 | B2 | B1 | C3
Yes | ENVIRONMENT | High wind | A high wind warning is defined as 1-minute average surface winds of 35 kt (40 mph or 64 km/hr) or greater lasting for 1 hour or longer, or winds gusting to 50 kt (58 mph or 93 km/hr) or greater regardless of duration that are either expected or observed over land. | Injury due to flying and/or dropped objects Productivity Loss | Weather Issues known, weather monitoring in place Selection of best vessel for environment Lose objects tied down secured Minimise human activities Identified high wind issues at Bid stage, weather down time in place | B1 | C3 | B1 | C3
Yes | ENVIRONMENT | Hurricane/Cyclone | A region of low atmospheric pressure. Also, a tropical storm. Note: Cyclones can be a few feet across or can be major storm systems such as hurricanes, tornadoes, and typhoons. Note: These winds move counter clockwise in the Northern Hemisphere and clockwise in the Southern Hemisphere. | Loss of productivity Potential Asset Damage Potential for injury/illness, minor to sever | Hazard identified at bid stage, weather down time in place Weather standby in contracts Evacuation procedures in place Weather monitoring in place Personnel aware of hazards/exposure minimised/movement in vessel minimised Motion medication available | B1 | C3 | B1 | C3
Yes | ENVIRONMENT | Fog | A dense layer of cloud lying close to the surface of the ground or water and reducing visibility to less than 1 km (0.62 mi). Fog occurs when the air temperature becomes identical, or nearly identical, to the dew point | Event due to restricted visibility: Road transport collision/third party interaction Vessel/Boat collision/third party interaction Loss of productivity | Management procedures for what to do during fog Safe working distances established Stop or minimise vehicle/boat movement during fog Weather monitoring Weather standby in contracts | B1 | C3 | B1 | C3
Yes | ENVIRONMENT | Precipitations (rain, snow, hail) | Precipitation is rain, snow, sleet, or hail — it is a kind of weather condition that can effect all outdoor activities, creating visibility issues and slip risks, can have the same effect as fog on vehicles and vessels. | Event due to restricted visibility Productivity loss and/or Asset loss | Minimise onshore outdoor activities Water proofing of external equipment Weather monitoring Weather standby in contracts Correct PPE | B1 | C3 | B1 | C3
Yes | ENVIRONMENT | Static electricity | Electric charge that has accumulated on an object. Static electricity is often created when two objects that are not good electrical conductors are rubbed together, and electrons from one of the objects rub off onto the other. This happens, for example, when combing one's hair or taking off a sweater. | Loss of asset/electronics fire | Earthling of electronic systems / utilise UPD Fuelling procedures have measures to dissipate static Availability of fire fighting equipment Circuit breakers in place / emergency cut-off | B1 | C2 | B1 | C2
Yes | ENVIRONMENT | Lightning | The occurrence of a natural electrical discharge of very short duration and high voltage between a cloud and the ground or within a cloud, accompanied by a bright flash and typically also thunder. Can cause Electronic/ Recording equipment, communication radios can be damaged during thunderstorm. Lightning can cause fire. Can cause harm to person exposed to it | Production loss due to weather standby, Potential for Asset Loss (Potential LWDC/Fatality if exposed) | Earthing of electronic systems / utilise UPD Procedures to switch of electrical appliance systems / Circuit breakers in place / emergency cut-off All personnel stay indoors (faraday protection) Weather standby in contracts | B1 | C3 | B1 | B2
Yes | ENVIRONMENT | Rough sea | Rough seas are choppy and turbulent, and might make you seasick. Difficult to navigate with small boats (capsizing), same for deployment/retrieval of OBC equipment. Personnel transfer, cross-decking and crane operations may be suspended. MOB and Medevac may become critical to deal with due to the strong heave. Seas breaking over vessel decks may damage equipment and lead to injury/MOB situation. No helicopter support. | Illness of staffs requiring MTC Financial impact due to reshoot because of noise Potential impact on subsea equipment | Weather forecast, MOPO, cross decking procedures, life jacket, severe weather monitoring plan. Weather standby in contracts BOISET Insurance Limited or no transfers of staffs during rough weather | B1 | C3 | B1 | C3
Yes | ENVIRONMENT | Tides | Tide is the vertical rise and fall of the water, Tides are the periodic motion of the waters of the sea due to changes in the attractive forces of the Moon and Sun upon the rotating Earth. Tides can either help or hinder a mariner. A high tide may provide enough depth to clear a bar, while a low tide may prevent entering or leaving a harbour | Loss productivity mainly due to low tides. Asset Damage due to striking sea floor/obstacle Injury's; FAC to LWDC | Tidal issues captured at Bid stage/SW down time for tides captured Sounder on vessels and boats Training of staffs in SW conditions LIDAR maps for SW activities MOPO, cross decking procedures, life jacket BOISET | B1 | C3 | B1 | C2
Yes | ENVIRONMENT | Slippery ground | Many accidents occur by slipping on wet or slippery floors, which can result in broken bones, examples of which are, Wet decks, oil spills not cleaned, Ice etc.… generally linked with precipitation | Injury's, from FAC to MTC mainly due to twists and/or sprains, can result in RWC/LWDC | Anti-slip solutions for slippery floors, stairs and other surfaces House Keeping removal of spills and grease accumulations in Galleys and workshops PPE (Boots) | B1 | B2 | B1 | C3
Yes | ENVIRONMENT | Flotsam | Flotsam is floating debris in water and can be responsible of collision with small boats and may cause MOB, equipment loss etc.. Particularly in Tropical regions, Larger vessels have been known to get entanglement in the DP propellers | Asset Damage Production Loss | Duty watch in place / communications Procedures in place to mange removal of propeller obstructions (Diving) Identified high risk areas such as river to sea access points | B1 | C3 | B1 | C1
Yes | ENVIRONMENT | Shallows | Shallow water presents some risks due to difficulty to evaluate depth of obstacles such as coral reefs. The risk to damage boats is high, which may result in equipment loss and possible drowning of personnel. Pollution. | Grounding of vessels, particularly the shallow water vessels | MOPO, LIDAR maps available Sounder on vessels and boats Maritime maps available Procures for oprtions in shallows in place/ area risk assessment done | C2 | C3 | B2 | C2
Yes | ENVIRONMENT | Visible obstacles | Something that ​blocks you so that ​movement, going ​forward, or ​action is ​prevented or made more ​difficult: Failure to communicate and emphasize on potential risks associated to the proximity of some obvious visible obstacle, Drilling Platforms, Flares, Third Party vessels. | Collision Fishing gear caught in seismic equipment Asset loss / damage | AIS All navigational systems working and up to date Vessel activity has been broadcasted to all vessels on project area Highlight obstacles during planning, Survey Area Maps, safe distances to be defined. Radar on vessel/boats, VHF radio communication, chase / support vessels, Coast Guard. | B3 | C3 | B3 | C2
Yes | ENVIRONMENT | Hidden obstacles | Concealed, not visible/unseen, generally for our marine environment hidden refers to subsurface obstacles or structures that can pose a threat to safe operations Failure to communicate and emphasize on potential risks associated to subsurface unseen obstacle, Well heads, Corals, pipe lines, military ordnance | Asset Loss Environmental Damage Reputation loss Potential for Injury | All subsurface obstacles in project area identified through Client, pipe lines wellhead etc... Environmental sensitive areas identified, corals / wreaks Safe anchoring zones established | B3 | C3 | B3 | C2
Yes | ENVIRONMENT | Security / robbery (money, equipment) | Use of force against individuals to get property, money: Assault, robbery/theft, abduction, threatening behaviour, intimidation, juvenile delinquency. | Potential physical injury, stolen money/credit cards | Communication with local authority to define sensitive areas Staffs informed of preventative measures through TIS Selection of Hotels in safe areas Reduce exposure by limiting unnecessary movement from hotel. | B3 | C3 | B1 | C3
Yes | ENVIRONMENT | Security / community | Local communities are often regarding our activities as a potential source of profit as well a source of disruption. Against all expectations, reactions can become violent with variable impact on our activities (vandalism / sabotage). Company may be involved with secular ethnic conflict. Poor communication with stakeholders, communities leaders. Labour strike gaining ground. | Potential physical injury, equipment and assets are liable to damages and vandalism action. | Avoid identified risky areas Communication with local authority to define sensitive areas / Permit team in place Contractual conditions to manage standby in place Security management and safe evacuation means in place Head office monitoring of threat issues Removal of targeted expatriated staff from onshore | C2 | C3 | B1 | C2
Yes | ENVIRONMENT | Security / civil unrest | Civil disturbance is typically a symptom of, and a form of protest against, major socio-political problems; the severity of the action coincides with public expression(s) of displeasure. Examples of civil disorder include, but are not necessarily limited to: illegal parades; sit-ins and other forms of obstructions; riots; sabotage; and other forms of crime. It is intended to be a demonstration to the public and the government, but can escalate into general chaos. | Potential physical injury, equipment and assets are liable to damages Ports blocked/No shore support available | Avoid identified risky areas Proper security assessment, deterrent security setup, protection Fleet communications and procedures Control through contract/tender analysis Professional Security Advise Head office monitoring of threat issues Contractual conditions to manage standby and/or evacuation in place | C3 | C3 | B1 | C2
Yes | ENVIRONMENT | Security / Piracy (terrorism) | An illegal act of violence, depredation (e.g., plundering, robbing, or pillaging), or detention in or over international waters committed for private ends by the crew or passengers of a private ship against another ship or against persons or property on board such ship. Transiting through country's with where there is a threat of terrorism particularly to westerners is equal to the risks of piracy. | Potential physical injury, Ransom demand, equipment and assets are liable to damages | Avoid identified risky areas decided at Board Level. Hardening of Vessels / Use of military Escort Fleet communications and procedures Control through contract/tender analysis Professional Security Advise Head office monitoring of threat issues Contractual conditions to manage standby and/or evacuation in place Journey management in place/controlled meet and greet City and hotel selection based on risk assessment | B4 | B4 | B1 | B4
Yes | EQUIPMENT | High noise / vibration generation | Noise is a variety of sound. It means any unwanted sound. Sounds, particularly loud ones, that disturb people or make it difficult to hear wanted sounds, potential causes: No sound proof machinery, deficient exhaust system, airgun firing, Noise generated vibrations, helicopter transport | Personnel can suffer Stress, Sleep deprivation and/or be aggressive Emergency alarms may be inaudible. | Noise Surveys Assessment of Vessels before Hiring Shift systems Acoustic Barriers, Low noise equipment , engineering controls PPE hearing protection | B3 | C2 | B1 | C2
Yes | EQUIPMENT | Deficient electrical systems | Electrical standards greatly differ from country to country and vessel to vessel. Electricity can be very harmful to people exposed to direct and/or indirect contact. Alteration / modification of electrical system (appliance, extension) is one of the main cause of fire in premises / vehicles. | Most common would be to have small electrical shock resulting in MTC (there is always the potential for Fatality) Asset Loss, replacement of electrical panels and boards | Safe work procedures in place, known Permit-to-Work Lock Out/Tag-Out Rubber matting at circuit breakers / emergency cut-off Authorised staffs only / training of staffs PPE | B3 | C3 | B3 | C2
| EQUIPMENT | Engine and/or Power supply failure (Vessel) | Loss of the main engine would lead to reduced speed and increase the risk for an equipment loss and damages to the in water equipment. Deficient electrical system can lead to partial / total black out and loss of propulsion. | Loss of Production Asset, potential need to change vessel | Vessels equipped with secondary systems Engines and machinery properly maintained. Engine room manned at all times. Emergency standby generator tested and available. scheduled maintenance Efficient Power Management System. Support vessel availability - training for emergency towing operations. Black out drills. Suitability audit for each vessel prior to employment | B2 | C3 | B1 | C1
| EQUIPMENT | Steering Failure (Vessel) Drifting | Loss of control of the ship can lead to a major equipment damage, not only to the vessel it's but surrounding facility's i.e. Platforms, flares… | Loss of Production Asset either vessel or third party damage Potential for environmental event | Emergency steering procedure. Redundancy of propulsion system Emergency steering procedure drills prior to the operation and conducted in compliance with ISM schedule (< 90 days) Emergency Towing procedure SOPEP | B2 | C3 | B3 | C2
Yes | EQUIPMENT | Hot surface and/or parts | Handling of hot parts and products (Galley, mechanic and other workshop, engines) may result in severe burns. | Injury's tendency with galley/workshop staffs resulting in MTC from touch hot surfaces | Thermal Barriers at Source. Barriers to access (PTW) Inspection windows Temperature Gauges PPE for task | B2 | C2 | B1 | C2
Yes | EQUIPMENT | High pressure system (Air/Hydraulic/Water) | Air guns with pressure up to at 2000 PSI. Uncontrolled release of air may cause blast, whip, projection of debris, impact or penetration with damage to equipment, and severe injuries to personnel. Whipping hoses / absence of safety clip. Danger of pressurized water is more due to projections rather than a whip hose | Injury's, from FAC to LWDC Asset Damage | Certifications of inspections Preventative Maintenance Schedules Restricted access / Warning lights and signals | B2 | C3 | B1 | C3
Yes | EQUIPMENT | Suspended equipment | Suspended load may fall down from hoisting device onto personnel and/or equipment causing serious accident with possible risk of spill (oil drum). Rupture with snapback. Momentum of suspended load during transfer may cause loss of control / collision. Non identified risk areas (warning signs). Unwanted presence of onlookers (lifting underway). | Injury's, from FAC to LWDC Asset Damage | Lift Plan, Permit-to-Work Sling & Strop Register Load Calculations Tag Lines Contractor management | B2 | C3 | B2 | C3
Yes | EQUIPMENT | Overhead obstacles / Falling equipment | Handling of heavy / awkward loads. Rupture of attachment point / deficient lifting equipment. Incorrect storage (box stacking). Inadequate cargo loading. Sling related failure. Main rotor of helicopter | Injury's, from FAC to LWDC Asset Damage | Work site Assessment Barriers to entry Hi-Viability Markings and Guards. | B2 | C3 | B2 | C3
Yes | EQUIPMENT | Tense, rotating equipment | Various equipment such , compressors, engines are equipped with tense chains or belts. Rupture of a such devices may cause serious injuries to people or damage to material. Whiplash from a broken spreading wire that was under tension Rotating parts , cable boat spooling drum, boat propellers, grinding machines, shafts, sprockets, pulleys can cause very serious injuries. | Injury's, from FAC to LWDC Asset Damage | Lock Out/Tag-Out Safe work procedures Maintenance controls | B2 | C3 | B2 | C3
Yes | EQUIPMENT | Erected object | Shrouded mast exposed to high wind. Lightning. Working at height. Falling equipment. Overhead power lines. Trip and fall onto sharp stumps (trekking). Boarding helicopter with poles in up position. | Injury's, from FAC to LWDC Asset Damage | Permit-to-Work Working at Height procedures Staffs trained /TRA | B2 | C3 | B2 | C3
Yes | EQUIPMENT | Poor lighting | Lack of illumination may cause trips and falls during transfers at sea, at quay side | Injury's, from FAC to LWDC MOB | Fixed lighting and portable lighting available Transfers in daylight-only operations. | B2 | C3 | B2 | C3
Yes | MATERIALS | Flammable and Combustible | Flammable and combustible liquids are liquids that can burn. They are classified, or grouped, as either flammable or combustible by their flashpoints. Generally speaking, flammable liquids will ignite (catch on fire) and burn easily at normal working temperatures. Combustible liquids have the ability to burn at temperatures that are usually above working temperatures. The flashpoint of a liquid is the lowest temperature at which the liquid gives off enough vapour to be ignited (start burning) at the surface of the liquid. | Injury's, from FAC to LWDC | Lower flash-point products Handled as per manufactures MSDS staffs trained on the use of product Fire fighting training, Sprinkler systems, alarms PPE | B2 | C3 | B2 | C3
Yes | MATERIALS | Highly flammable | A Highly Flammable Liquid (HFL) is a liquid with a flash point below 32 deg C. The flash point of a liquid is the lowest temperature at which the liquid can evaporate to produce vapour in sufficient concentration to form a combustible mixture with air near the surface of the liquid The Flash point is not the temperature at which a substance will ignite spontaneously. It is an indication of the ease with which a substance will burn if the vapours are exposed to a temperature at or above its auto-ignition temperature. | Injury's, from FAC to LWDC | Substitution of product for less harmful Lower flash-point products Handled as per manufactures MSDS staffs trained on the use of product Used in well ventilated areas PPE | B2 | C3 | B2 | C3
Yes | MATERIALS | Carcinogenic, Mutagenic, Reprotoxic materials | A carcinogen, mutagenic and reprotoxic are any substance, radionuclide, or radiation that is an agent directly involved in causing cancer. This may be due to the ability to damage the genome or to the disruption of cellular metabolic processes. | Long term Illness, potentially fatal | Substitution of product for less harmful Obtain Asbestos free certificates for vessels Handled as per manufactures MSDS Increase awareness and knowledge of crew supervisors in the management of hazardous materials | B1 | B3 | B1 | B3
Yes | MATERIALS | Highly toxic | Highly toxic (T+) products are very small quantities of substances which, by inhalation, ingestion or skin contact, expose to very high risks, acute or chronic, until death.H2S gas is an example. | Illness/nausea due to inhalation/ingestion requiring medical intervention | Substitution of product for less harmful Handled as per manufactures MSDS/Training staffs trained on the use of product Used in well ventilated areas H2S detection devices installed on every vessel + portative detectors for small boat operations. H2S emergency breathing masks provided. PPE | B2 | C3 | B2 | C3
Yes | MATERIALS | Toxic | Toxic (T) products are small quantities of substances which, by inhalation, ingestion or skin contact, expose to high risks, acute or chronic, and sometimes death. | Injury's, from FAC to LWDC | Substitution of product for less harmful Handled as per manufactures MSDS/Training staffs trained on the use of product Used in well ventilated areas PPE | B2 | C3 | B2 | C3
Yes | MATERIALS | Corrosive and harmful | Harmful (Xn) products are substances which, by inhalation, ingestion or skin contact, expose to risks with limited gravity. Corrosive (C) products destroy living tissues. | Injury's, from FAC to LWDC Environment damage | Substitution of product for less harmful Handled as per manufactures MSDS COSSH assessment staffs trained on the use of product Used in well ventilated areas PPE for task | B2 | C3 | B2 | C3
Yes | MATERIALS | Irritant | Irritant (Xi) products are non corrosive substances, which , by immediate, prolonged or repeated contact with the skin or mucous membranes will cause an inflammatory reaction. Dangerous for skin, specially for eyes and mucous membrane in form of liquid. Vapours can also irritate the lungs and respiratory tracks. | Injury's, from FAC to LWDC | Substitution of product for less harmful Handled as per manufactures MSDS COSSH assessment staffs trained on the use of product Used in well ventilated areas PPE | B2 | C3 | B2 | C3
Yes | PROCESS | Road Transport / Traffic Event | There are many issues linked with road transport, top issues effecting road transport are, but not limited too: Driver behaviour, Over speeding, Third party traffic and driving in poor conditions can lead to collisions, parking and manoeuvring | Injury's from FAC to Fatality Asset Loss and replacement | Apply Road Transport management standard Apply Road Transport Compliance Contractor Management Insurance Vehicle selection standards Training: DC | B2 | C3 | C2 | B5
Yes | PROCESS | Overloaded and/or Sudden movement of boat (SW vessels) | Boat not suitable for encountered conditions (rough sea, stem wave). Personnel on-board crushed or falling onto fixed deck object. Uneven weight distribution. Overloaded boat. No passenger discipline on board of small craft. No adequate protection from falling overboard (guard rails, hand holds and harnesses). | Interaction with small third party craft susceptible to capsizing, resulting asset/financial loss. Violation of regulations leading to a fine Medical attention required | MOB plan (Search Rescue) Boat seletction and risk assessment to ensure suitablity MOPO in place / Procedures for personnel transfer / Stop work authority Weather monitoring Boats controled, POB respected /Load management and planning BOSIET / Fixed guard rails | B2 | C3 | B1 | B3
Yes | PROCESS | Man overboard | Personnel accidentally falling into water. Multiple MOB. No adequate protection from falling overboard (guard rails, hand holds, harnesses / open slipways). Vessel life saving appliances not maintained in a state of readiness at all time. Fall from the back deck or fall from a small boat at sea. | Medical attention required for water ingestion MTC and/or Fatality | Use of Personal Locator Beacon Life Jackets On Board Training: safety induction tours. Buddy system Fall arrester for open back deck operations Demarcation zones for using fall arrestors. | B2 | B2 | B1 | B3
Yes | PROCESS | Colliding | Sinkage. Damage to vessels / fishing gear / jetty. Abandonment / personnel transfer. | Injury's from FAC to Fatality Asset Loss Environment pollution | AIS monitoring. Bridge management Good communication | B2 | C3 | B2 | C3
Yes | PROCESS | Grounding | Structural damage. Abandonment. Pollution. Injury to personnel on impact. | Asset loss Injury's, from FAC to LWDC | AIS monitoring. Bridge management Good communication | B2 | C3 | B2 | C3
Yes | PROCESS | Helicopter Emergency (Ditching) | Engine failure over water causing emergency landing of the aircraft. Pilot decision to re-route for emergency landing. | Injury's from FAC to Fatality Loss of Asset Environment pollutant Reputation, Media attention | BOSIET / HUET SWTC95 minimum for marine crew Contractor Management / Audit of helicopter company Weather monitoring Helicopter induction video Helicopter audited / All maintemcve schedules maintained Fuel checked for water contamination | B4 | B5 | B2 | B5
Yes | PROCESS | Incorrect use of ladders and scaffolding | Poor design / stability to support load. Step ladders used as straight ladder. No safety feet and rubber tips for extension and straight ladder. Use of conductive ladder for electrical work. Working at height / aloft. Poor supervision / no PTW. Falling items / poor control of access (onlookers). | Injury's, to fingers due to miss handling, resulting in MTC Severity of traetment from fall linked to height | Design of work areas, avoiding items that need to be reached by ladders Ladders seleted suitable for task Instruction on the use of ladders | B1 | B2 | B1 | C3
Yes | PROCESS | Working aloft | For personnel performing tasks (de-rusting, painting ...) above water, whatever on-board a vessel / quay the risk of falling into water and drowning is severe. If the life line is not properly fastened, the risk of hanging over, head down, exists. | Generaly MTC due to foirign object in the eye, but failure of fall system can result severer injury | Approved Fall Protection PTW and procedures in place Training on procedures and equipment use Only authorised staffs | B1 | B3 | B1 | B4
Yes | PROCESS | Working at height | Various situation may call for personnel to be working at height e.g. antenna installation, maintenance on vessels / tanks / vibrators / roof type air conditioner etc. These activities are propitious to falls with severe injury if not death. Awkward supports / not proof tested or maintained. Use of ladders. Incorrect posture. PTW. Subcontracted work. | Failure of fall system can result severe injury leading to LWDC (potential of fatality) | Approved Fall Protection PTW and procedures in place Training on procedures and equipment use Only authorised staffs | B1 | B3 | B1 | B4
Yes | PROCESS | Manual handling | Many items to be lifted are too heavy or awkward to hold for one person. Presence of grease for instance increase the risk of mishandling / falling. No provision for lifting device / trolleys (workshop). Insufficient number of people to carry equipment along the line. Transportable equipment design | Injury's requiring MTC treatment, finger entrapment, small back injury | Reduce weight of items that need to be moved Substitute for Mechanical handling means Carry by two people, Do not handle more than 30kg alone Ergonomics training / Communication Staff selection for task (Height/Strength) | A2 | A2 | A2 | E2
Yes | PROCESS | Working on active system | Lock out / tag out while maintenance is underway. Pressure hose safety clip (whipping effect). Authorized personnel / PTW / supervision. No notice / warning signs. | Injury's requiring MTC treatment Loss/damge to Asset | PTW / MOPO / Lock out Tag Out Planned maintenance during technical stops specific tasks dedicated to specialised subcontractors | B2 | C3 | B2 | C3
Yes | PROCESS | Working in confined spaces | insufficient lighting and oxygen as well as restricted means of escape could lead to phobia and erratic behaviour. Poor ventilation in confined spaces could result in the build up of hazardous gases resulting in possible explosion or asphyxiation. PTW. | Without control potential Fatality Finaniacl loss | Avoid entrance or work in confined spaces PTW / MOPO / Lock out Tag Out gas testers - air blowers - breathing apparatus. Buddy system. | B2 | B3 | B1 | B4
Yes | PROCESS | Insufficient control of access | Security of premises / installation / facilities. Prevention from intruders / thieves. Restricted access to hazardous working areas. | Unauthorized access leading to equipment theft or damage | Hotel/camp and agency locations in respectable neighbourhood Onshore workshops have access control and security Good crew change management ISPS implementation on-board Security implemented during port calls Radar offshore to identify any vessel/boat approach | B2 | C3 | B1 | C3
Yes | PROCESS | Housekeeping & Insufficient segregation of hazards | Poor housekeeping may contribute to trips and falls, blocking access to emergency equipment / exit, propagation of fire. It may impair the detection of leaks and defaults. Multiple consequences possible, overlapping with other hazards in the register: trips and falls, falling objects, poor access to (emergency) equipment, fire and electrical hazards, sharp/protruding objects. Poor housekeeping reflects a poor attitude towards HSE, but also re-enforces this poor attitude. It also gives a very poor impression of the workplace to visitors and clients. | Common issue of minor injurys requiring MTC, generally linked to trips | Optimize materials and equipment in terms of ease of storage, number of lose components etc. Ensure good workplace design, with ample storage facilities, good work benches and adequate floor space. Avoid having uneven floors, tripping hazards, sharp and protruding or low objects. | B3 | C3 | B1 | C3
Yes | PROCESS | Lack of access to emergency equipment / lack of emergency exits | Delay finding / reaching emergency bag, water pump / fire hose, extinguisher, eyes wash station, first aid box, fire blanket, emergency cut-off switch, alarm etc. Housekeeping considerations (obstruction) and signs posting (disorientation) may be crucial at the very first stage of an emergency. | This can increase the likelihood and severity of otherwise controlled risks. | Well thought of and design placement of emergency equipment. Emergency cut off switches and valves. ERP in place and tested frequently. SOPEP available, suitable and sufficient All signage as per IMO standard Regular inspections of all emergency needs | B3 | B3 | C3 | C3
Yes | PROCESS | Crane and Hoisting Operations / Deficiency with attachment points | Lack of capacity signs (SWL ratings). Non qualified operator. Lack of supervision. No test / inspection on working condition of conditions of stop of limit switches. Deficient equipment / non serviceable. The Working Load Limit is the maximum load which should ever be applied to the product, even when the product is new and when the load is uniformly applied - straight line pull only. Avoid side loading However, while the definition for working load limit was originally confined exclusively to the manufacturer&#8217;s specified maximum load that the item could lift, it is now generally extended to include both of the following: the maximum load that an item can lift the maximum load that an item can lift in a particular configuration or application. All lifting equipment must nave appropriate capacity signs (Safe Working Limit / Working Load Limit ratings) | PTD/LWDC due to entrapment whilst manoeuvring load (Potential Fatality if load dropped) | Mechanical load handling remains preferred over manual handling , so be cautious with elimination. Keep area free of personnel . Adequate selection and design of lifting and hoisting equipment. Reduce weight of equipment/materials needed. | B3 | C3 | C2 | C3
Yes | PROCESS | Diving Operations | Drowning. Negative attitude towards HSE rules. Lack of specialist / inadequate selection. No in-water repair training. No dedicated rescue craft for in water tasks. Typical hazards, Propeller obstruction / Hull integrity Checks, Offshore Facility's & Tourist dives | Stop of production due to diving activities Potential of Entrapment of diver (drowning) | Professional Dive company / Certified divers Safe zones for diving identified / currents and tides identified Risk assessment done by Dive company / Safe working procedures available Offshore platforms informed of Seismic shooting activities / safety distances respected Local dive business and tourist community's aware of seismic activities | B3 | B3 | B1 | C3
Yes | PROCESS | Interacting with local culture | Seismic activity often require contact with local population, Despite the immediate benefit brought to local economics, adverse effects may occur, factors to be considered, No competence to handle public relations (and media). Interaction with local culture not clearly organised with clients or contractors. Third party activities and interaction with fishing vessels/boats can lead to disputes and stoppage of seismic activates. | Disputes with local fishermen most common Community unrest due to unacceptable behaviour of staffs | Avoid mixing personnel from groups in conflict ( tribal, regional, religious). Community management plan. Local recruitment strategies. Local communication and stakeholder management strategy. Keep camp location away from settlements, "Offshore" policy for non local personnel: confine to camp - no contact with local community. Qualified community liaison officers. | B3 | B3 | B2 | B3
Yes | PEOPLE | Previous recurrent injury / disease | Some injuries, whatever from previous domestic or work origin, such as dislocation can often reoccur during lifting operations. Recurrent diseases could also break out , directly linked to work activity or not; in some cases food or water contamination is possible, as well as contagion. | Employee becomes unfit to work NWR injury/illness becomes work related due to work activities | Pre medical check Medical questionnaire to identify individuals at risk | B3 | C3 | B1 | C3
Yes | PEOPLE | Fatigue / stress | Individuals, on a daily basis, may be exposed to various and numerous factors which will increase fatigue and stress, especially when recovering and resting is not sufficient or when it conflicts with professional or personal targets. Then they cannot allocate proper vigilance and pay attention to their tasks. | This could result in minor injuries, or in extreme case, be one of the causes of an accident with fatalities. Can result in loss of equipment or pollution release | Limit time spent in noisy environment Design of facilities to reduce stressful conditions / accommodations in quiet zones Regular breaks from routine tasks. Crew change and shift patterns to enable rest after travelling. | B3 | C3 | B3 | C3
Yes | PEOPLE | Not medically or physically fit | Failure to recognise unfit stakeholders can lead to injuries not only to themselves but others, The need replace or evacuate staffs unfit for tasks of their job description or to work offshore can have serious financial impact. Risk are normally accosted with Eyesight, Unfit body, Abnormal size, poor limb coordination | Loss of work due to illness/injury and replacement of staffs | Pre employment medical check UGUK Management of contractors/Clients to ensure recognised medical checks are in place | B2 | C3 | B1 | C3
Yes | PEOPLE | Reaction to medicine | In some cases, patients get allergic reactions to some drugs, changing a basic medical treatment into serious emergency. | Medical treatment will be needed, probably off site, can lead to LWDC and be potentially fatal Loss of production to evacuate | Medical records and history held on project by medic and/or Captain(confidential). Alternative medication held on project. Fully stocked hospital. 24 hour emergency line to doctor/hospital, Emergency response plan | B2 | C3 | B1 | C3
Yes | PEOPLE | Negative attitude toward HSE rule | In many cases, a known HSE rules is violated. This "I don't want" or "I cannot" attitude may be linked to various reasons and not necessarily linked to a sole individual. But a negative attitude toward HSE rule may trigger catastrophic accident scenario. | Injury's due to staffs taking short cuts or loss of asset | Training and induction of staffs to HSE Culture Implementation of consequence management Frequent site/workshop visits and walk rounds by management focusing on behaviour Implementation of BBS | B3 | B3 | B2 | B3
Yes | PEOPLE | Ergonomics (Human) | An incorrect posture or wrong position, can cause injury and be related to long term injury/illness, linked with manual handling. People working permanently in offices or workshops where they are desk bound due to bad seating position may also, on long term, induce back injuries. | Most common is lower back complaints | Office/workshop ergonomics issues identified, information passed to staffs Provide improved workstation ergonomics. Prevent hunching over laptop by supply 2nd adjustable screens Adjustable work surfaces. | B3 | B3 | B3 | C2
Yes | PEOPLE | Underestimation of risk and/or Overconfidence | The underestimation of risk poses the added risk of increased potential for loss. When persons do not understand the full characteristics of the risk before them, they are then led to make decisions based on their interpretations of the risk. Overconfidence is seen in many accident scenarios as a factor linked to the underestimation of risk due to routine tasks or young and inexperienced personnel (need to be proved) | Standdown required due to failure to manaage risk approperately resulting in financial loss Injurys can occur | Training and Mentoring / Implimentation of SSE program Review of TRA involvment in meetings Experienced supervision | B3 | C3 | B3 | C3
Yes | PEOPLE | Self medication and/or none disclosed medical condition | Staffs may have medincics that could result in an inability to function correctly, impairing safety of operations for personnel with sensitive positions. Obvious needs for the medicine is the treatment of medical conditions that may also result in a persons inability to function currently and put others at risk | Evacuation of employee due to none work lasted issue / financial Loss | Self medication should be eliminated as it impacts one's reactions and their ability to perform. Communication to Project Doctors and medical teams Disclosure in pre medical | B3 | C3 | B2 | C3
Yes | PEOPLE | Alcohol or drug abuse | Alcohol and drug abuse, by altering perception and behaviour may lead to highly hazardous situation , especially for personnel conducting critical activities (drivers, crane operators, pilots ...). | Injury's due to inattention caused by alcohol or drugs | Apply the SBGS Policy on Alcohol and drug abuse Intermittent tests for all stakeholders Consequence management applied | B3 | C3 | B1 | C3
Yes | PEOPLE | Life style choice | Some staffs choose life styles that can effect their work due to Ill health effects associated with their life style choice. Examples of the most common Smoking, non-healthy diet, Alcohol/drugs, lack of exercise These choices also at times have impact on others | Leading to time off work, due to Illness or injury (Heat attack most common) Has the potential to cut short a persons offshore working ability | Medical and Physical examinations (Fit to Work) Controlled diets on projects Posters and awareness on the ill health effects of smoking, drinking, poor diet and non exercise Supply exercise equipment Implement healthy life style / assist persons with their addictions | B3 | B3 | B3 | C3
Yes | PEOPLE | Panicking in emergency | Personnel can panic and lose control in a fire situation especially if seeing fire for the first time, or abandonment in difficult weather conditions, especially helicopter ditching. Personnel can panic and lose control of a serious injury situation. It may be the first time they have witnessed injury and pain. | Injury's ranging from FAC to LWDC (in extreme emergency's could be fatal) | Training and awareness Regular drills and exercises Ensure competency experience of key positions, (i.e. Masters, Pilots etc.…) | B3 | B4 | B3 | B4
Yes | PEOPLE | Trips / falls (ground level) | Any small ground obstacle may unbalance people walking through/past this obstacle, then sometimes falling on hazardous areas or sharp objects that they are carrying. On-board boats, vessels, continuous movement may easily unbalance the personnel, causing falls in exiguous and often hazardous places. | Minor injury's from FAC to MTC | Identification of trip hazards / markiong of trip hazards Handrails where steps are concerned for three points of contact. | B1 | B2 | B1 | C3
Yes | MANAGEMENT | PPE Selections and/or Maintenance | The associated risk with all individual tasks and operations is significantly enhanced if incorrect, defective or inadequate protective clothing and/or equipment is provided to accomplish the task. This will includes inadequate personal protective equipment (PPE) and maintenance of that equipment | Poor selection, improper use and inadequate maintenance of PPE can be an escalating factor increasing the likelihood of injury | PPE seletcion to a known standard Maintained as per manufactures instructions Personnel informaed and instructed on the use of PPE Consequence management applied for violation of PPE | B3 | C3 | B3 | C3
Yes | MANAGEMENT | Deficient machinery guard | All rotating machinery has to be considered as a serious risk of accident. Fingers, long hair, loose clothes may be caught by any rotating piece and generate a serious accident (contusion, lost of fingers ...). | Partial Permanent Disability, most common finger crushed | Ensure all guards are fit for purpose / working / inplace Part of inspection schedule Staffs informed of the risks of entrapment | B3 | C3 | B3 | C3
Yes | MANAGEMENT | Deficient maintenance | A good maintenance is the key to avoid problems on any kind of equipment. Preventive maintenance has to be considered as a real priority. A lack of maintenance or deficiency in maintenance may result in a failure of equipment when you must need it or when you are operating it. | As most of managerial factors in incident causation sequences, this hazard, associated to others, may indirectly lead to events with multiples fatalities and / or massive financial or reputation loss and / or catastrophic environmental consequences. | Reduction t maintenance by training / use of competent personnel, Engineering controls: design or procure equipment with regard to reduced maintenance requirements, Good spares levels maintained. Use of specialized third company maintenance personnel / services | B3 | C3 | C3 | C3
Yes | MANAGEMENT | Poorly designed equipment | The equipment (machinery, apparatus, gear, craft, vehicle ...) does not fulfil the function for which it was purchased. The equipment must be suitable to the work environment and then adequately designed for its use's purpose. A poorly design equipment may easily lead to major accidents. | Most likely outcome, financial loss due to removing non-functional equipment and paying replacment Injury can occur, severity pending type of equipment | Design equipment to known standards Involvment of HSE at design stage Testing equipment prior to mobilising | B3 | C3 | B3 | C2
Yes | MANAGEMENT | Deficient emergency / recovery planning | If the accident finally occurs, consequences may be very different depending on the level of preparation. A deficient emergency plan, disorganization may result in permanent disability or death. A non adapted recovery equipment or badly used may have the same consequences. | Failure leading to major loss In three key area, People/Financial/Environment | Inspection of HSE safety critical equipment Identification of required safety critical equipment/maintained and in working order to EU/OSHA/IMO requirements Ensure emergency plans are suitable for all foreseeable emergencys reviewed and tested regulary | B3 | C3 | C3 | C3
Yes | MANAGEMENT | Communication & Language deficiency's | Communications are a necessary operational requirement for both routine and emergency operations. A bad communication network affects immediately the quality of journey management and effectiveness of emergency responses; worse, a major accident may stay unworn several hours, delaying all recovery processes. Many different languages may be used on a crew. Misunderstanding of instructions, procedures, etc.. due to the difference of language between people may become the causes of accidents (lack of knowledge on how to operate). | Injury's due to poorly communicated information Loss of Asset/Production | Daily operational meetings. Defined organogram and communication hierarchy list. Provision of Scope of work and Project plan to Master and ROV PM (OVM). Language should be in English through all radio conversations. Use posters, signs and mix crews to enable common language. | B2 | B3 | A1 | C3
Yes | MANAGEMENT | Deficient Medical Equipment / Medicines and Qualified Staffing | Remote operations require a particular attention to the medical welfare afforded on projects, lack of medical equipment or medicine, can have serious consequences, additionally the staffing staffing needs to be such that can help and stabilise in remote locations. | Failure to stabilise IP or to impiment medical evacuation Impact financially due to evacuation of IP | Medical Supplier contract in place, covering staffing, equipment and medicines (full package) Medical supplier management Medicine under medical supplier MERP done by supplier and sufficient for remote risk. | B3 | C3 | B1 | C3
Yes | MANAGEMENT | Inadequate and/or insufficient selection of personnel | Inadequate personnel, i.e. badly trained, informed, unfit or insufficiently educated for a particular job may be the source of root causes of accident by lack of knowledge or competency. and can lead to extra work because of those inadequacies . Overload of work due to an insufficient number of personnel will increase by excess of tiredness, stress, risks of accident of any kinds | Can lead to stress and conflicts between staffs | Implementation of contractor management Selection of the right person for the tasks, i.e. through use of CV Ensure at project start skill levels and quantity's of staffs required are foreseen | B3 | C3 | B3 | C3
Yes | MANAGEMENT | Training deficiency Lack of Competency and/or certified personnel | Deficient personnel training prior to any kind of job may cause accidents by lack of knowledge on how to operate (vehicles, vessels, cranes, tools...), especially functions linked to critical activities. The bad use of the recovery equipment available (extinguisher, fire blanket, ...) may cause an extra accident in addition the bad use of safety equipment and PPE are effectively useless if crews do not know how to operate or wear them correctly .Many specialized tasks need personnel with specific competency, training and licensing and certified for that task, i.e. Master, Doctor | Finical impact of having to train contractors who should have the certification and/or replacement of staffs without certification | Training done at all levels, SBGS and project Follow up in SBGS on line training data base Identified key areas where certification is required, ensure certificate are followed at project level. Implementation of contractor management | B3 | C3 | B2 | C3
Yes | MANAGEMENT | Inadequate selection / management of subcontractor / Subcontractor Contracts | On a seismic crew, significant part of the activity is conducted by subcontractors (ship managers , chase vessels, ship yards , etc..). A poor process of evaluation, selection and follow up may jeopardize the safety of any operation managed by a subcontractor if they do not apply proper HSE standards and policies. If the terms of the contract between SBGS and its subcontractors do not clearly detail all requirements, the subcontractors may not identify gaps and then not bring a proper answer, creating a lack of resources and/or inadequate standards. | Lager fincail losses due to poor contractor management Injury's from FAC to Fatality Asset Loss Environment pollution | Major subcontractors (operating at risk activities such as ship managers, medical support suppliers,...) are evaluated and assessed against SBGS "contractor management" procedure. Good selection process managed onshore (SBGS Crewing and HR Manager): Recruitment of subcontracted personnel is based on assessment of their qualification, experience and trainings. Bridging interface document with subcontractors. Inductions given on site Information, training, instruction and supervision all given on site | B3 | C4 | B3 | C3
Yes | MANAGEMENT | Deficient information | A lack of communication to the project , especially information from the head office or the clients, may deprive the project of critical information to start. If the meetings are not properly planned, prepared and conducted, the needed HSE information is not given at the right time to the right persons. | Porject start delays is the most common issue with deficent information | Organisational structure understood by all stake holders Meeting schedules set Video conferances used as tool for remote assistance | B3 | B3 | B1 | B1
Yes | MANAGEMENT | Project Planning deficiency | Failure to follow proper planning methodology at tender and contract review stage and failing to implement the full scope of PEP (Project Execution Plan), at mobilization stage inadaquauate resources, standards and inappropriate methods being applied. | Loss of reputation with client Financial impact due to foreseen issues failing to be managed | Lead time for planning during bid stage, planning meetings, monitoring of planning stages, communication at all levels. PEP responsibility's defined, completed as scheduled as per contractual agreement. HAZID pre survey meeting / Pre Start up meetings ERP in place prior to mobilisation, tested after mobilisation. | C3 | C4 | B3 | B3
Yes | MANAGEMENT | Reporting deficiency | Failure of post accident reporting, including near misses, does not allow to conduct pertinent analysis and bring adequate corrective actions, promoting reoccurrence of accident scenarios. A poor reporting of positive activity does not allow implementation of preventative program to allow continuous improvement of the HSE management system. | Client complaints the most likley | Follow up of all events as per classification Impose management review, to ensure Top management involvement Follow strictly the SBGS event reporting process | B3 | B2 | B1 | B2
Yes | MANAGEMENT | Inspection / control deficiency | When activities and equipment are not properly inspected, non-conformities and unsafe conditions are not detected, offering preconditions to numerous accident scenarios. | Injury from FAC to PTD Asset Loss | Reduction of hazards by identification and implementation of Inspection routines. Inspection routines defined, Inspection and monitoring devices available and in good working order (sensors, pressure gauges etc.) | B3 | C3 | C3 | C3
Yes | MANAGEMENT | Deficient Event Investigation | When post incident investigations are not properly conducted, the quality of corrective actions do not prevent from reoccurrence. Sometimes, incidents with low consequences but potentially high consequences are not identified as such and then do not allow decisions and actions to be taken by competent parties. In addition, a lack of investigation after controls and inspections let unsafe conditions not being corrected by proper remedial actions. | Client complaints due to superficial investigation Failure to identify the root cause | Ensure a system of investigation follow up is implemented and agreed | C3 | B3 | B3 | B3
Yes | MANAGEMENT | Deficient Procedures / Work instruction and TRA's | A key aspect to assess hazards and conduct safely activities is to capture who is doing what and when in written procedures and work instructions: when they do not exist, are inaccurate or not communicated, learning are lost, new people not aware or practices are gradually changing, offering basement for catastrophic scenario. | Loss of productivity and/or asset due to poor safe work systems Can lead to injury's | Procedures written and approved at corporate level, in accordance with OMS operational policies Work instructions written and approved at project level (not overriding corporate procedure Regular review of TRA's by HOD / Creation of new TRA's by HOD | B3 | C3 | B3 | C3
Yes | MANAGEMENT | Insufficient travel / journey management | When journey management rules for air, water or land transport are not properly applied, the immediate detection of hazardous situations is affected. This can be staffs travel from home to project, or localised JM in country and around projects | Staffs lost on arrival in country, risks to the traveler not managed | Project TIS implemented for all travelling employees and delivered to contractor/clients. Phone contacts known Specific follow up of commercial staffs traveling to identified Risk Areas Transportation of staffs within country and/or project correctly monitored. | B2 | B2 | B2 | C3
Yes | MANAGEMENT | Inadequate definition of responsibilities | When HSE responsibilities are not clearly defined first in job descriptions and secondly in the execution of a project, and as of tender stage, we may expect some shortcomings in the planning and implementation. | Persons without authority effecting project/company matters | Bid and tender team set / responsibility's known Job description available on project inclusive of contractors and Clients on project. Responsibility's entered into all corporate procedures Organisational Charts, Corporate and at Project level, available and followed. | C3 | C4 | B1 | C2
Yes | MANAGEMENT | Inadequate definition of standard | Every time we design equipment, purchase equipment and goods, define work method and subcontract expertise ; if we do not integrate a clear reference to agreed HSE standards in our design specifications, purchasing data, quality processes, call for tender documents ; we may conduct operations with hazardous equipment, practices and/or breaking laws | Financial impact due to replacing non-standard products | Apply the SBGS known/agreed standards found in Guardian Measure standards against that of contractual agreement and/or Industry requirement Vessels to follow international standards (e.g. IMO /SOLAS / MARPOL etc. Identification of legal and legislation local requirements | B3 | C3 | A3 | B3
Yes | MANAGEMENT | Evaluation & risk management | Risk management is a main component of an efficient HSE system, taking place at all level of the organization, every time this risk assessment is not conducted or poorly realized, we expose our personnel and activities to non-recognized hazards, unplanned situations and / or inadequate controls and recoveries. | Financialand reputation loss due to not identifying foreseeable hazards that later cause downtime | HAZID Workshops pre mobilisation Project Risk assessments completed for foreseeable risks | C3 | B3 | B3 | C3
Yes | MANAGEMENT | Conflict of interest | Sometimes, production needs and HSE constraints are contradictory. To preserve presence on the market, when seismic companies are selected only on price criteria, operating standards are decreased as of tender stage. Some contract terms may generate conflict of interest, especially when heavy penalties are linked to mobilisation and/or downtime by clients, obliging crews to operate at the border of permitted operations. | Previous arrangements not available causing late start and penalty's applied | To negotiate penalty out of contact or decrease impact at bid stage and/or establish incentives by client. Contractor management | C4 | C4 | B1 | B3
Yes | MANAGEMENT | Audit & Review deficiency | If operations are not audited by their management or specialists, major deficiencies will not be identified. All HSE activity is measured with various indicators, pro-active or reactive, against predefined objectives and programs if management reviews are not or poorly organized to review the HSE performance, feedback will not be communicated, momentum will be lost | Reputation failing to meet contractual agreement | Implementation of auditing, Qualified/experienced auditors and selected observers. Use of standard auditing tools across company. Audits implemented from third parties. Actions and training to enable correct reviewing of audits, lessons learned from investigations (including identification of causal / root cause analysis). Document and procedure review, review of statistical information that may highlight deficiencies within organization | C3 | B3 | B1 | B1

## Project Risk
SBGS Specific Risk Register_Type: OBN
|  |  |  | Client: Chevron | Project:
Docummet Details
Version: |  | 1
Date Created |  | 2015-07-21
Next Review |  | 2015-09-21
Approved By:
Area Risk Ratings ( Risidual Risk Rating)
Applicable Yes/No | Hazard Category | Hazard Basic Description | Hazard Generic Description | Identified Hazard Specfic to Project | Potential Consequence (Most Likely Outcome's) | Control Measures Prevention & Mitigation | Control Measures Additional and/or Specfic Procedure/plan | Reputation | Assets / Financial | Environment | People | Responsible Department
Yes | ENVIRONMENT | Threats from Invertebrate | Some invertebrate species can be harmful to people, and many of the world's most dangerous parasites are members of the invertebrate family. Some of the more well-known invertebrate parasites include ticks, fleas, and leeches. Some invertebrates, like mosquitoes, can be especially damaging because they can potentially carry diseases. The most common marine invertebrates are sponges, cnidarians, marine worms, lophophorates, molluscs, arthropods, echinoderms and the hemichordates | The risk is very limited but during gun arrays or baskets/ROV + TMS recovery, there is the possibility to bring back a sea snake or Jelly Fish on-board the vessel. Having the personnel not wearing their PPE / not aware about the risk even if limited and night operations will increase the risk of personnel injury. | Injury or occupational illness ranging from FAC and/or MTC/RWC being the most likely realistic outcome | Project awareness via safety meetings and TBM. Good lighting aboard the vessels and onto ROV / Basket / source arrays during recovery. Personnel equipped with proper PPE. Staffs/Contractors with updated vaccinations up to date Anti-venom availability Mosquito control in hotels/use of AC/sprays/Information about malaria available | Crew awareness via safety meeting and TBM. Good lighting aboard the vessels and onto ROV / Basket / source arrays during recovery. Personnel equipped with proper PPE. Awareness training to be conducted by crew Medic | B2 | B2 | B1 | C3 | Party Manager
No | ENVIRONMENT | Threats from Vertebrate | There are many thousands of species of vertebrate that have the potential to be harmful to humans, either attacking with tooth and claw or causing harm though poison/venom, common examples encountered by human interaction off/onshore: Dogs, reptiles, cats, fish. |  | Injury or occupational illness ranging from FAC and/or MTC/RWC being the most likely realistic outcome | Care and attention, onshore and at hotel facility's - Information via TIS. Staffs/Contractors with updated vaccinations up to date Identified hazardous species, awareness campaigns Anti-venom availability if required |  | B2 | B2 | B1 | C3
No | ENVIRONMENT | Infectious disease | Infectious diseases are disorders caused by organisms — such as bacteria, viruses, fungi or parasites. Many organisms live in and on our bodies. They're normally harmless or even helpful, but under certain conditions, some organisms may cause disease. Some infectious diseases can be passed from person to person. |  | Isolations and/or medical evacuation of infected staff, resulting in financial loss Infected staffs with MTC illness, likelihood of LWDC. | All personnel are carrying up to date UKOOA / NMD medical certificates. Enforce practices that reduce the likelihood of exposure: appropriate procedures for hand washing, sharps disposing, laundry handling & contaminated material cleaning. Provide personal protective equipment such as gloves, gowns, and masks. Disposable gloves available in all first aid kits. |  | B1 | C3 | B1 | C3
No | ENVIRONMENT | Intestinal parasites | Intestinal parasites are parasites that can infect the gastro-intestinal tract of humans and other animals. Means of exposure include: ingestion of undercooked meat, drinking infected water, and skin absorption. |  | Injury or occupational illness ranging from FAC and/or MTC being the most likely realistic outcome | Ensure all meats are correctly cooked Reporting system to ensure undercooked meats are identified Food handling training for galley team to be held by crew medics Personal hygiene recommended practices known Use only bottled water or water that has been analysed fit to drink |  | B1 | C2 | B1 | C2
No | ENVIRONMENT | Contaminated food and water | Ingestion of contaminated fresh water or food by different microbes or pathogens agents. Vomiting, diarrhoea, stomach cramps, fever, nausea, headache, in rare cases potentially fatal Food not checked by Medic No water testing No Food handler medical examination for cooks and galley team. Poor Selection of contractors (Ship chandler) Improper food handling and hygiene on-board. No respect of Ship Managers' internal procedures , No respect of OGP Waste Management Guidelines, IAGC Marine Geophysical Manual |  | Occupational illness of multiple persons on board, ranging from FAC to LWDC being the most likely realistic outcome Replacement of catering contractor | Water analyses performed UV filtration installed on the main water systems. Food handler medical examination for cooks and galley team & Food handling training for galley team. Selection of contractors/contractor management. Food handling and hygiene on-board in camps, monitored. Health and hygiene inspections carried out every week by crew by medics. Garbage Management plan in place aboard all vessels involved in the survey |  | B1 | C3 | B1 | C3
No | ENVIRONMENT | Exposure to Air Pollutant (Natural Gas & H2s) | Natural gas is a hydrocarbon gas mixture consisting primarily of methane, but commonly includes varying amounts of other higher alkanes and sometimes a usually lesser percentage of carbon dioxide, nitrogen, and/or hydrogen sulphide. Natural gas is an energy source often used for heating, cooking, and electricity generation. It is also used as fuel for vehicles Hydrogen sulphide (also known as H2S, Sour Gas) is colourless, toxic and flammable gas and is partially responsible for the foul odour of rotten eggs and flatulence. Hydrogen sulphide is both an irritant and an asphyxiate gas and can cause death |  | Occupational illness of multiple persons on board, ranging from FAC to LWDC being the most likely realistic outcome, Potential of fatality's have been known pending parts per million dosage | Identification of types of gas i.e. Carbon Monoxide, H2s H2s Training, and /or other pending gas Identification Alarm and monitoring systems, vessel and personal, based on the identified gas and risks Awareness controls such as meetings and posters Carbon monoxide detectors in high risk area. |  | B1 | B3 | B1 | B4
No | ENVIRONMENT | Extreme cold weather | Extreme Cold refers to the condition or subjective perception of having low temperature, the absence of heat, extreme cold can cause Hypothermia is life threatening in some instance i.e. long immersion in cold water, but most common scenario are personal working hard (sweating) and then resting in icy conditions (pneumonia). |  | Staffs with cold and flue symptoms requiring MTC Asset Loss, due to hose breakage etc... | Reduced exposure through shorter shifts Instruction and Information on extreme cold environments Training on identification of cold related injury's including frostbite Physical fitness of staffs exposed Correct clothing PPE for the environment Mechanical systems checked / hoses inspected / Antifreeze utilised |  | B1 | C3 | B1 | C3
No | ENVIRONMENT | Extreme heat weather | High temperature constitutes a real risk to personnel which results in fatigue, dehydration, and eventually failure of thermal regulating mechanism: The faint symptoms come first, followed by cramps then comes the heat exhaustion and eventually the heat stroke (life threatening). Immersion syncope. Food poisoning situation is more likely to occur under warm climates due to quicker food decomposition. |  | Staffs requiring MTC due to over heating Asset Loss due to over heating | Reduced exposure through shorter shifts / ensure sufficient water consumption Food monitoring place / controlled by caterer Instruction and Information on extreme heat environments Training on identification of heat related disorders Physical fitness of staffs exposed Correct clothing PPE for the environment Mechanical cooling systems checked / Ventilation systems check |  | B1 | B3 | B1 | C3
No | ENVIRONMENT | Cold water | The definition of cold water is variable. The temperature of thermally neutral water, in which heat loss balances heat production i.e., not shivering, is approximately 33-35° C. Hypothermia eventually results from immersion in water below this temperature, significant risk of immersion hypothermia usually begins in water colder than 25° C. Cold water immersion is associated with two significant medical emergencies: near drowning and hypothermia |  | Staffs with cold and flue symptoms requiring MTC Potential of being enerced in cold water could result in fatality | MOB system in place efficient for cold environment Fall arresters and guard rails in place Hazardous areas with risk of overboard marked and monitored / No lone workers Correct clothing PPE for the environment |  | B1 | B2 | B1 | C3
No | ENVIRONMENT | High wind | A high wind warning is defined as 1-minute average surface winds of 35 kt (40 mph or 64 km/hr) or greater lasting for 1 hour or longer, or winds gusting to 50 kt (58 mph or 93 km/hr) or greater regardless of duration that are either expected or observed over land. |  | Injury due to flying and/or dropped objects Productivity Loss | Weather Issues known, weather monitoring in place Selection of best vessel for environment Lose objects tied down secured Minimise human activities Identified high wind issues at Bid stage, weather down time in place |  | B1 | C3 | B1 | C3
Yes | ENVIRONMENT | Hurricane/Cyclone | A region of low atmospheric pressure. Also, a tropical storm. Note: Cyclones can be a few feet across or can be major storm systems such as hurricanes, tornadoes, and typhoons. Note: These winds move counter clockwise in the Northern Hemisphere and clockwise in the Southern Hemisphere. | The Australian Cyclone season runs from November and ends in April, average for western Australia is 7 cyclones during the season | Loss of productivity Potential Asset Damage Potential for injury/illness, minor to sever | Hazard identified at bid stage, weather down time in place Weather standby in contracts Evacuation procedures in place Weather monitoring in place Personnel aware of hazards/exposure minimised/movement in vessel minimised Motion medication available | Familiarize all personnel hurricane preparedness procedures Post hurricane tracking chart Monitor via different media any hurricane activities. Distribute and discuss weather forecasts with all department heads. For duration of hurricane season, all loose equipment that will not be used in the course of normal operations should remain secured. Vessels Masters to monitor hurricanes / cyclones and to take decision to escape to shelter areas. | B1 | C3 | B1 | C3 | Vessel Master
No | ENVIRONMENT | Fog | A dense layer of cloud lying close to the surface of the ground or water and reducing visibility to less than 1 km (0.62 mi). Fog occurs when the air temperature becomes identical, or nearly identical, to the dew point |  | Event due to restricted visibility: Road transport collision/third party interaction Vessel/Boat collision/third party interaction Loss of productivity | Management procedures for what to do during fog Safe working distances established Stop or minimise vehicle/boat movement during fog Weather monitoring Weather standby in contracts |  | B1 | C3 | B1 | C3
No | ENVIRONMENT | Precipitations (rain, snow, hail) | Precipitation is rain, snow, sleet, or hail — it is a kind of weather condition that can effect all outdoor activities, creating visibility issues and slip risks, can have the same effect as fog on vehicles and vessels. |  | Event due to restricted visibility Productivity loss and/or Asset loss | Minimise onshore outdoor activities Water proofing of external equipment Weather monitoring Weather standby in contracts Correct PPE |  | B1 | C3 | B1 | C3
No | ENVIRONMENT | Static electricity | Electric charge that has accumulated on an object. Static electricity is often created when two objects that are not good electrical conductors are rubbed together, and electrons from one of the objects rub off onto the other. This happens, for example, when combing one's hair or taking off a sweater. |  | Loss of asset/electronics fire | Earthling of electronic systems / utilise UPD Fuelling procedures have measures to dissipate static Availability of fire fighting equipment Circuit breakers in place / emergency cut-off |  | B1 | C2 | B1 | C2
No | ENVIRONMENT | Lightning | The occurrence of a natural electrical discharge of very short duration and high voltage between a cloud and the ground or within a cloud, accompanied by a bright flash and typically also thunder. Can cause Electronic/ Recording equipment, communication radios can be damaged during thunderstorm. Lightning can cause fire. Can cause harm to person exposed to it |  | Production loss due to weather standby, Potential for Asset Loss (Potential LWDC/Fatality if exposed) | Earthing of electronic systems / utilise UPD Procedures to switch of electrical appliance systems / Circuit breakers in place / emergency cut-off All personnel stay indoors (faraday protection) Weather standby in contracts |  | B1 | C3 | B1 | B2
Yes | ENVIRONMENT | Rough sea | Rough seas are choppy and turbulent, and might make you seasick. Difficult to navigate with small boats (capsizing), same for deployment/retrieval of OBC equipment. Personnel transfer, cross-decking and crane operations may be suspended. MOB and Medevac may become critical to deal with due to the strong heave. Seas breaking over vessel decks may damage equipment and lead to injury/MOB situation. No helicopter support. | ea conditions causing delay or damage to equipment or injury to personnel during deployment and recovery of source arrays / Nodes' basket / Remotely Operated Vehicle (ROV) + Tether Management System (TMS). Poor / no weather forecast. No respect of MOPO. Poor Operations Planning Poor Communications Unfamiliar procedures or procedures not followed Lack of experience with deployment / recovery of gun arrays. Perceived time pressures to achieve task leading to precipitation Sea sickness / Fatigue. Personnel loosing balance. Equipment not properly secured Personnel falling over board during array deployment/recovery | Illness of staffs requiring MTC Financial impact due to reshoot because of noise Potential impact on subsea equipment | Weather forecast, MOPO, cross decking procedures, life jacket, severe weather monitoring plan. Weather standby in contracts BOISET Insurance Limited or no transfers of staffs during rough weather | Experienced Personnel Manual Handling training TRA and WI / procedures in place and understood by all personnel. Good Communication + TBM Proper Housekeeping routines Cross Inspections Gun Deck Inspection checklist Certification, Inspection and Maintenance Coaching / buddy system Multiple sources for weather forecasts / Weather monitoring Controlled build-up of operational practices / experience - no rushing. Start-up meeting with crew stress no time constraints and safety of people and equipment important. Stop - Step Back - Re-assess - Find safe way to proceed. Clear line management. 3 points contact rules: Use of life jacket and fall arrestor (life line). Daily Operational and Tool Box Meetings General MOPO & Nodes operation MOPO. ObsWI216V1 Node handling in adverse weather Source deployment and retrieval GPS-0006 Source operations GPS-0001 ROV called winch launch and recovery procedures FROV-Ref1400 ROV Operations Manual Hugin ROV procedure CEP-0001 Emergency Response Vessel | B1 | C3 | B1 | C3 | Vessel Master
No | ENVIRONMENT | Tides | Tide is the vertical rise and fall of the water, Tides are the periodic motion of the waters of the sea due to changes in the attractive forces of the Moon and Sun upon the rotating Earth. Tides can either help or hinder a mariner. A high tide may provide enough depth to clear a bar, while a low tide may prevent entering or leaving a harbour |  | Loss productivity mainly due to low tides. Asset Damage due to striking sea floor/obstacle Injury's; FAC to LWDC | Tidal issues captured at Bid stage/SW down time for tides captured Sounder on vessels and boats Training of staffs in SW conditions LIDAR maps for SW activities MOPO, cross decking procedures, life jacket BOISET |  | B1 | C3 | B1 | C2
No | ENVIRONMENT | Slippery ground | Many accidents occur by slipping on wet or slippery floors, which can result in broken bones, examples of which are, Wet decks, oil spills not cleaned, Ice etc.… generally linked with precipitation |  | Injury's, from FAC to MTC mainly due to twists and/or sprains, can result in RWC/LWDC | Anti-slip solutions for slippery floors, stairs and other surfaces House Keeping removal of spills and grease accumulations in Galleys and workshops PPE (Boots) |  | B1 | B2 | B1 | C3
No | ENVIRONMENT | Flotsam | Flotsam is floating debris in water and can be responsible of collision with small boats and may cause MOB, equipment loss etc.. Particularly in Tropical regions, Larger vessels have been known to get entanglement in the DP propellers |  | Asset Damage Production Loss | Duty watch in place / communications Procedures in place to mange removal of propeller obstructions (Diving) Identified high risk areas such as river to sea access points |  | B1 | C3 | B1 | C1
No | ENVIRONMENT | Shallows | Shallow water presents some risks due to difficulty to evaluate depth of obstacles such as coral reefs. The risk to damage boats is high, which may result in equipment loss and possible drowning of personnel. Pollution. |  | Grounding of vessels, particularly the shallow water vessels | MOPO, LIDAR maps available Sounder on vessels and boats Maritime maps available Procures for oprtions in shallows in place/ area risk assessment done |  | C2 | C3 | B2 | C2
No | ENVIRONMENT | Visible obstacles | Something that ​blocks you so that ​movement, going ​forward, or ​action is ​prevented or made more ​difficult: Failure to communicate and emphasize on potential risks associated to the proximity of some obvious visible obstacle, Drilling Platforms, Flares, Third Party vessels. |  | Collision Fishing gear caught in seismic equipment Asset loss / damage | AIS All navigational systems working and up to date Vessel activity has been broadcasted to all vessels on project area Highlight obstacles during planning, Survey Area Maps, safe distances to be defined. Radar on vessel/boats, VHF radio communication, chase / support vessels, Coast Guard. |  | B3 | C3 | B3 | C2
Yes | ENVIRONMENT | Hidden obstacles | Concealed, not visible/unseen, generally for our marine environment hidden refers to subsurface obstacles or structures that can pose a threat to safe operations Failure to communicate and emphasize on potential risks associated to subsurface unseen obstacle, Well heads, Corals, pipe lines, military ordnance | Identified near the project area is a military training area for live round tests , there is a potential, although highly unlikely possibility of a UXO presence on the sea floor | Asset Loss Environmental Damage Reputation loss Potential for Injury | All subsurface obstacles in project area identified through Client, pipe lines wellhead etc... Environmental sensitive areas identified, corals / wreaks Safe anchoring zones established | Chevron provide a brief report stating the results of any anomalies discovered during the marine seismic survey that may represent Unexploded Ordnance Suspect Item’s should not be touched (by ROV or subsurface equipment Its location and general appearance, size and any other relevant information (including images if identified by ROV) should be reported | B3 | C3 | B3 | C2 | Chevron Defence: Brian Barkworth (UXO@defence.gov.au) ROV pilot Vessel Masters
No | ENVIRONMENT | Security / robbery (money, equipment) | Use of force against individuals to get property, money: Assault, robbery/theft, abduction, threatening behaviour, intimidation, juvenile delinquency. |  | Potential physical injury, stolen money/credit cards | Communication with local authority to define sensitive areas Staffs informed of preventative measures through TIS Selection of Hotels in safe areas Reduce exposure by limiting unnecessary movement from hotel. |  | B3 | C3 | B1 | C3
No | ENVIRONMENT | Security / community | Local communities are often regarding our activities as a potential source of profit as well a source of disruption. Against all expectations, reactions can become violent with variable impact on our activities (vandalism / sabotage). Company may be involved with secular ethnic conflict. Poor communication with stakeholders, communities leaders. Labour strike gaining ground. |  | Potential physical injury, equipment and assets are liable to damages and vandalism action. | Avoid identified risky areas Communication with local authority to define sensitive areas / Permit team in place Contractual conditions to manage standby in place Security management and safe evacuation means in place Head office monitoring of threat issues Removal of targeted expatriated staff from onshore |  | C2 | C3 | B1 | C2
No | ENVIRONMENT | Security / civil unrest | Civil disturbance is typically a symptom of, and a form of protest against, major socio-political problems; the severity of the action coincides with public expression(s) of displeasure. Examples of civil disorder include, but are not necessarily limited to: illegal parades; sit-ins and other forms of obstructions; riots; sabotage; and other forms of crime. It is intended to be a demonstration to the public and the government, but can escalate into general chaos. |  | Potential physical injury, equipment and assets are liable to damages Ports blocked/No shore support available | Avoid identified risky areas Proper security assessment, deterrent security setup, protection Fleet communications and procedures Control through contract/tender analysis Professional Security Advise Head office monitoring of threat issues Contractual conditions to manage standby and/or evacuation in place |  | C3 | C3 | B1 | C2
No | ENVIRONMENT | Security / Piracy (terrorism) | An illegal act of violence, depredation (e.g., plundering, robbing, or pillaging), or detention in or over international waters committed for private ends by the crew or passengers of a private ship against another ship or against persons or property on board such ship. Transiting through country's with where there is a threat of terrorism particularly to westerners is equal to the risks of piracy. |  | Potential physical injury, Ransom demand, equipment and assets are liable to damages | Avoid identified risky areas decided at Board Level. Hardening of Vessels / Use of military Escort Fleet communications and procedures Control through contract/tender analysis Professional Security Advise Head office monitoring of threat issues Contractual conditions to manage standby and/or evacuation in place Journey management in place/controlled meet and greet City and hotel selection based on risk assessment |  | B4 | B4 | B1 | B4
No | EQUIPMENT | High noise / vibration generation | Noise is a variety of sound. It means any unwanted sound. Sounds, particularly loud ones, that disturb people or make it difficult to hear wanted sounds, potential causes: No sound proof machinery, deficient exhaust system, airgun firing, Noise generated vibrations, helicopter transport |  | Personnel can suffer Stress, Sleep deprivation and/or be aggressive Emergency alarms may be inaudible. | Noise Surveys Assessment of Vessels before Hiring Shift systems Acoustic Barriers, Low noise equipment , engineering controls PPE hearing protection |  | B3 | C2 | B1 | C2
No | EQUIPMENT | Deficient electrical systems | Electrical standards greatly differ from country to country and vessel to vessel. Electricity can be very harmful to people exposed to direct and/or indirect contact. Alteration / modification of electrical system (appliance, extension) is one of the main cause of fire in premises / vehicles. |  | Most common would be to have small electrical shock resulting in MTC (there is always the potential for Fatality) Asset Loss, replacement of electrical panels and boards | Safe work procedures in place, known Permit-to-Work Lock Out/Tag-Out Rubber matting at circuit breakers / emergency cut-off Authorised staffs only / training of staffs PPE |  | B3 | C3 | B3 | C2
No | EQUIPMENT | Engine and/or Power supply failure (Vessel) | Loss of the main engine would lead to reduced speed and increase the risk for an equipment loss and damages to the in water equipment. Deficient electrical system can lead to partial / total black out and loss of propulsion. |  | Loss of Production Asset, potential need to change vessel | Vessels equipped with secondary systems Engines and machinery properly maintained. Engine room manned at all times. Emergency standby generator tested and available. scheduled maintenance Efficient Power Management System. Support vessel availability - training for emergency towing operations. Black out drills. Suitability audit for each vessel prior to employment |  | B2 | C3 | B1 | C1
No | EQUIPMENT | Steering Failure (Vessel) Drifting | Loss of control of the ship can lead to a major equipment damage, not only to the vessel it's but surrounding facility's i.e. Platforms, flares… |  | Loss of Production Asset either vessel or third party damage Potential for environmental event | Emergency steering procedure. Redundancy of propulsion system Emergency steering procedure drills prior to the operation and conducted in compliance with ISM schedule (< 90 days) Emergency Towing procedure SOPEP |  | B2 | C3 | B3 | C2
No | EQUIPMENT | Hot surface and/or parts | Handling of hot parts and products (Galley, mechanic and other workshop, engines) may result in severe burns. |  | Injury's tendency with galley/workshop staffs resulting in MTC from touch hot surfaces | Thermal Barriers at Source. Barriers to access (PTW) Inspection windows Temperature Gauges PPE for task |  | B2 | C2 | B1 | C2
No | EQUIPMENT | High pressure system (Air/Hydraulic/Water) | Air guns with pressure up to at 2000 PSI. Uncontrolled release of air may cause blast, whip, projection of debris, impact or penetration with damage to equipment, and severe injuries to personnel. Whipping hoses / absence of safety clip. Danger of pressurized water is more due to projections rather than a whip hose |  | Injury's, from FAC to LWDC Asset Damage | Certifications of inspections Preventative Maintenance Schedules Restricted access / Warning lights and signals |  | B2 | C3 | B1 | C3
No | EQUIPMENT | Suspended equipment | Suspended load may fall down from hoisting device onto personnel and/or equipment causing serious accident with possible risk of spill (oil drum). Rupture with snapback. Momentum of suspended load during transfer may cause loss of control / collision. Non identified risk areas (warning signs). Unwanted presence of onlookers (lifting underway). |  | Injury's, from FAC to LWDC Asset Damage | Lift Plan, Permit-to-Work Sling & Strop Register Load Calculations Tag Lines Contractor management |  | B2 | C3 | B2 | C3
No | EQUIPMENT | Overhead obstacles / Falling equipment | Handling of heavy / awkward loads. Rupture of attachment point / deficient lifting equipment. Incorrect storage (box stacking). Inadequate cargo loading. Sling related failure. Main rotor of helicopter |  | Injury's, from FAC to LWDC Asset Damage | Work site Assessment Barriers to entry Hi-Viability Markings and Guards. |  | B2 | C3 | B2 | C3
No | EQUIPMENT | Tense, rotating equipment | Various equipment such , compressors, engines are equipped with tense chains or belts. Rupture of a such devices may cause serious injuries to people or damage to material. Whiplash from a broken spreading wire that was under tension Rotating parts , cable boat spooling drum, boat propellers, grinding machines, shafts, sprockets, pulleys can cause very serious injuries. |  | Injury's, from FAC to LWDC Asset Damage | Lock Out/Tag-Out Safe work procedures Maintenance controls |  | B2 | C3 | B2 | C3
No | EQUIPMENT | Erected object | Shrouded mast exposed to high wind. Lightning. Working at height. Falling equipment. Overhead power lines. Trip and fall onto sharp stumps (trekking). Boarding helicopter with poles in up position. |  | Injury's, from FAC to LWDC Asset Damage | Permit-to-Work Working at Height procedures Staffs trained /TRA |  | B2 | C3 | B2 | C3
No | EQUIPMENT | Poor lighting | Lack of illumination may cause trips and falls during transfers at sea, at quay side |  | Injury's, from FAC to LWDC MOB | Fixed lighting and portable lighting available Transfers in daylight-only operations. |  | B2 | C3 | B2 | C3
No | MATERIALS | Flammable and Combustible | Flammable and combustible liquids are liquids that can burn. They are classified, or grouped, as either flammable or combustible by their flashpoints. Generally speaking, flammable liquids will ignite (catch on fire) and burn easily at normal working temperatures. Combustible liquids have the ability to burn at temperatures that are usually above working temperatures. The flashpoint of a liquid is the lowest temperature at which the liquid gives off enough vapour to be ignited (start burning) at the surface of the liquid. |  | Injury's, from FAC to LWDC | Lower flash-point products Handled as per manufactures MSDS staffs trained on the use of product Fire fighting training, Sprinkler systems, alarms PPE |  | B2 | C3 | B2 | C3
No | MATERIALS | Highly flammable | A Highly Flammable Liquid (HFL) is a liquid with a flash point below 32 deg C. The flash point of a liquid is the lowest temperature at which the liquid can evaporate to produce vapour in sufficient concentration to form a combustible mixture with air near the surface of the liquid The Flash point is not the temperature at which a substance will ignite spontaneously. It is an indication of the ease with which a substance will burn if the vapours are exposed to a temperature at or above its auto-ignition temperature. |  | Injury's, from FAC to LWDC | Substitution of product for less harmful Lower flash-point products Handled as per manufactures MSDS staffs trained on the use of product Used in well ventilated areas PPE |  | B2 | C3 | B2 | C3
No | MATERIALS | Carcinogenic, Mutagenic, Reprotoxic materials | A carcinogen, mutagenic and reprotoxic are any substance, radionuclide, or radiation that is an agent directly involved in causing cancer. This may be due to the ability to damage the genome or to the disruption of cellular metabolic processes. |  | Long term Illness, potentially fatal | Substitution of product for less harmful Obtain Asbestos free certificates for vessels Handled as per manufactures MSDS Increase awareness and knowledge of crew supervisors in the management of hazardous materials |  | B1 | B3 | B1 | B3
No | MATERIALS | Highly toxic | Highly toxic (T+) products are very small quantities of substances which, by inhalation, ingestion or skin contact, expose to very high risks, acute or chronic, until death.H2S gas is an example. |  | Illness/nausea due to inhalation/ingestion requiring medical intervention | Substitution of product for less harmful Handled as per manufactures MSDS/Training staffs trained on the use of product Used in well ventilated areas H2S detection devices installed on every vessel + portative detectors for small boat operations. H2S emergency breathing masks provided. PPE |  | B2 | C3 | B2 | C3
No | MATERIALS | Toxic | Toxic (T) products are small quantities of substances which, by inhalation, ingestion or skin contact, expose to high risks, acute or chronic, and sometimes death. |  | Injury's, from FAC to LWDC | Substitution of product for less harmful Handled as per manufactures MSDS/Training staffs trained on the use of product Used in well ventilated areas PPE |  | B2 | C3 | B2 | C3
No | MATERIALS | Corrosive and harmful | Harmful (Xn) products are substances which, by inhalation, ingestion or skin contact, expose to risks with limited gravity. Corrosive (C) products destroy living tissues. |  | Injury's, from FAC to LWDC Environment damage | Substitution of product for less harmful Handled as per manufactures MSDS COSSH assessment staffs trained on the use of product Used in well ventilated areas PPE for task |  | B2 | C3 | B2 | C3
No | MATERIALS | Irritant | Irritant (Xi) products are non corrosive substances, which , by immediate, prolonged or repeated contact with the skin or mucous membranes will cause an inflammatory reaction. Dangerous for skin, specially for eyes and mucous membrane in form of liquid. Vapours can also irritate the lungs and respiratory tracks. |  | Injury's, from FAC to LWDC | Substitution of product for less harmful Handled as per manufactures MSDS COSSH assessment staffs trained on the use of product Used in well ventilated areas PPE |  | B2 | C3 | B2 | C3
No | PROCESS | Road Transport / Traffic Event | There are many issues linked with road transport, top issues effecting road transport are, but not limited too: Driver behaviour, Over speeding, Third party traffic and driving in poor conditions can lead to collisions, parking and manoeuvring |  | Injury's from FAC to Fatality Asset Loss and replacement | Apply Road Transport management standard Apply Road Transport Compliance Contractor Management Insurance Vehicle selection standards Training: DC |  | B2 | C3 | C2 | B5
No | PROCESS | Overloaded and/or Sudden movement of boat (SW vessels) | Boat not suitable for encountered conditions (rough sea, stem wave). Personnel on-board crushed or falling onto fixed deck object. Uneven weight distribution. Overloaded boat. No passenger discipline on board of small craft. No adequate protection from falling overboard (guard rails, hand holds and harnesses). |  | Interaction with small third party craft susceptible to capsizing, resulting asset/financial loss. Violation of regulations leading to a fine Medical attention required | MOB plan (Search Rescue) Boat seletction and risk assessment to ensure suitablity MOPO in place / Procedures for personnel transfer / Stop work authority Weather monitoring Boats controled, POB respected /Load management and planning BOSIET / Fixed guard rails |  | B2 | C3 | B1 | B3
No | PROCESS | Man overboard | Personnel accidentally falling into water. Multiple MOB. No adequate protection from falling overboard (guard rails, hand holds, harnesses / open slipways). Vessel life saving appliances not maintained in a state of readiness at all time. Fall from the back deck or fall from a small boat at sea. |  | Medical attention required for water ingestion MTC and/or Fatality | Use of Personal Locator Beacon Life Jackets On Board Training: safety induction tours. Buddy system Fall arrester for open back deck operations Demarcation zones for using fall arrestors. |  | B2 | B2 | B1 | B3
No | PROCESS | Colliding | Sinkage. Damage to vessels / fishing gear / jetty. Abandonment / personnel transfer. |  | Injury's from FAC to Fatality Asset Loss Environment pollution | AIS monitoring. Bridge management Good communication |  | B2 | C3 | B2 | C3
No | PROCESS | Grounding | Structural damage. Abandonment. Pollution. Injury to personnel on impact. |  | Asset loss Injury's, from FAC to LWDC | AIS monitoring. Bridge management Good communication |  | B2 | C3 | B2 | C3
No | PROCESS | Helicopter Emergency (Ditching) | Engine failure over water causing emergency landing of the aircraft. Pilot decision to re-route for emergency landing. |  | Injury's from FAC to Fatality Loss of Asset Environment pollutant Reputation, Media attention | BOSIET / HUET SWTC95 minimum for marine crew Contractor Management / Audit of helicopter company Weather monitoring Helicopter induction video Helicopter audited / All maintemcve schedules maintained Fuel checked for water contamination |  | B4 | B5 | B2 | B5
No | PROCESS | Incorrect use of ladders and scaffolding | Poor design / stability to support load. Step ladders used as straight ladder. No safety feet and rubber tips for extension and straight ladder. Use of conductive ladder for electrical work. Working at height / aloft. Poor supervision / no PTW. Falling items / poor control of access (onlookers). |  | Injury's, to fingers due to miss handling, resulting in MTC Severity of traetment from fall linked to height | Design of work areas, avoiding items that need to be reached by ladders Ladders seleted suitable for task Instruction on the use of ladders |  | B1 | B2 | B1 | C3
No | PROCESS | Working aloft | For personnel performing tasks (de-rusting, painting ...) above water, whatever on-board a vessel / quay the risk of falling into water and drowning is severe. If the life line is not properly fastened, the risk of hanging over, head down, exists. |  | Generaly MTC due to foirign object in the eye, but failure of fall system can result severer injury | Approved Fall Protection PTW and procedures in place Training on procedures and equipment use Only authorised staffs |  | B1 | B3 | B1 | B4
No | PROCESS | Working at height | Various situation may call for personnel to be working at height e.g. antenna installation, maintenance on vessels / tanks / vibrators / roof type air conditioner etc. These activities are propitious to falls with severe injury if not death. Awkward supports / not proof tested or maintained. Use of ladders. Incorrect posture. PTW. Subcontracted work. |  | Failure of fall system can result severe injury leading to LWDC (potential of fatality) | Approved Fall Protection PTW and procedures in place Training on procedures and equipment use Only authorised staffs |  | B1 | B3 | B1 | B4
No | PROCESS | Manual handling | Many items to be lifted are too heavy or awkward to hold for one person. Presence of grease for instance increase the risk of mishandling / falling. No provision for lifting device / trolleys (workshop). Insufficient number of people to carry equipment along the line. Transportable equipment design |  | Injury's requiring MTC treatment, finger entrapment, small back injury | Reduce weight of items that need to be moved Substitute for Mechanical handling means Carry by two people, Do not handle more than 30kg alone Ergonomics training / Communication Staff selection for task (Height/Strength) |  | A2 | A2 | A2 | E2
No | PROCESS | Working on active system | Lock out / tag out while maintenance is underway. Pressure hose safety clip (whipping effect). Authorized personnel / PTW / supervision. No notice / warning signs. |  | Injury's requiring MTC treatment Loss/damge to Asset | PTW / MOPO / Lock out Tag Out Planned maintenance during technical stops specific tasks dedicated to specialised subcontractors |  | B2 | C3 | B2 | C3
No | PROCESS | Working in confined spaces | insufficient lighting and oxygen as well as restricted means of escape could lead to phobia and erratic behaviour. Poor ventilation in confined spaces could result in the build up of hazardous gases resulting in possible explosion or asphyxiation. PTW. |  | Without control potential Fatality Finaniacl loss | Avoid entrance or work in confined spaces PTW / MOPO / Lock out Tag Out gas testers - air blowers - breathing apparatus. Buddy system. |  | B2 | B3 | B1 | B4
No | PROCESS | Insufficient control of access | Security of premises / installation / facilities. Prevention from intruders / thieves. Restricted access to hazardous working areas. |  | Unauthorized access leading to equipment theft or damage | Hotel/camp and agency locations in respectable neighbourhood Onshore workshops have access control and security Good crew change management ISPS implementation on-board Security implemented during port calls Radar offshore to identify any vessel/boat approach |  | B2 | C3 | B1 | C3
No | PROCESS | Housekeeping & Insufficient segregation of hazards | Poor housekeeping may contribute to trips and falls, blocking access to emergency equipment / exit, propagation of fire. It may impair the detection of leaks and defaults. Multiple consequences possible, overlapping with other hazards in the register: trips and falls, falling objects, poor access to (emergency) equipment, fire and electrical hazards, sharp/protruding objects. Poor housekeeping reflects a poor attitude towards HSE, but also re-enforces this poor attitude. It also gives a very poor impression of the workplace to visitors and clients. |  | Common issue of minor injurys requiring MTC, generally linked to trips | Optimize materials and equipment in terms of ease of storage, number of lose components etc. Ensure good workplace design, with ample storage facilities, good work benches and adequate floor space. Avoid having uneven floors, tripping hazards, sharp and protruding or low objects. |  | B3 | C3 | B1 | C3
No | PROCESS | Lack of access to emergency equipment / lack of emergency exits | Delay finding / reaching emergency bag, water pump / fire hose, extinguisher, eyes wash station, first aid box, fire blanket, emergency cut-off switch, alarm etc. Housekeeping considerations (obstruction) and signs posting (disorientation) may be crucial at the very first stage of an emergency. |  | This can increase the likelihood and severity of otherwise controlled risks. | Well thought of and design placement of emergency equipment. Emergency cut off switches and valves. ERP in place and tested frequently. SOPEP available, suitable and sufficient All signage as per IMO standard Regular inspections of all emergency needs |  | B3 | B3 | C3 | C3
No | PROCESS | Crane and Hoisting Operations / Deficiency with attachment points | Lack of capacity signs (SWL ratings). Non qualified operator. Lack of supervision. No test / inspection on working condition of conditions of stop of limit switches. Deficient equipment / non serviceable. The Working Load Limit is the maximum load which should ever be applied to the product, even when the product is new and when the load is uniformly applied - straight line pull only. Avoid side loading However, while the definition for working load limit was originally confined exclusively to the manufacturer&#8217;s specified maximum load that the item could lift, it is now generally extended to include both of the following: the maximum load that an item can lift the maximum load that an item can lift in a particular configuration or application. All lifting equipment must nave appropriate capacity signs (Safe Working Limit / Working Load Limit ratings) |  | PTD/LWDC due to entrapment whilst manoeuvring load (Potential Fatality if load dropped) | Mechanical load handling remains preferred over manual handling , so be cautious with elimination. Keep area free of personnel . Adequate selection and design of lifting and hoisting equipment. Reduce weight of equipment/materials needed. |  | B3 | C3 | C2 | C3
No | PROCESS | Diving Operations | Drowning. Negative attitude towards HSE rules. Lack of specialist / inadequate selection. No in-water repair training. No dedicated rescue craft for in water tasks. Typical hazards, Propeller obstruction / Hull integrity Checks, Offshore Facility's & Tourist dives |  | Stop of production due to diving activities Potential of Entrapment of diver (drowning) | Professional Dive company / Certified divers Safe zones for diving identified / currents and tides identified Risk assessment done by Dive company / Safe working procedures available Offshore platforms informed of Seismic shooting activities / safety distances respected Local dive business and tourist community's aware of seismic activities |  | B3 | B3 | B1 | C3
No | PROCESS | Interacting with local culture | Seismic activity often require contact with local population, Despite the immediate benefit brought to local economics, adverse effects may occur, factors to be considered, No competence to handle public relations (and media). Interaction with local culture not clearly organised with clients or contractors. Third party activities and interaction with fishing vessels/boats can lead to disputes and stoppage of seismic activates. |  | Disputes with local fishermen most common Community unrest due to unacceptable behaviour of staffs | Avoid mixing personnel from groups in conflict ( tribal, regional, religious). Community management plan. Local recruitment strategies. Local communication and stakeholder management strategy. Keep camp location away from settlements, "Offshore" policy for non local personnel: confine to camp - no contact with local community. Qualified community liaison officers. |  | B3 | B3 | B2 | B3
No | PEOPLE | Previous recurrent injury / disease | Some injuries, whatever from previous domestic or work origin, such as dislocation can often reoccur during lifting operations. Recurrent diseases could also break out , directly linked to work activity or not; in some cases food or water contamination is possible, as well as contagion. |  | Employee becomes unfit to work NWR injury/illness becomes work related due to work activities | Pre medical check Medical questionnaire to identify individuals at risk |  | B3 | C3 | B1 | C3
No | PEOPLE | Fatigue / stress | Individuals, on a daily basis, may be exposed to various and numerous factors which will increase fatigue and stress, especially when recovering and resting is not sufficient or when it conflicts with professional or personal targets. Then they cannot allocate proper vigilance and pay attention to their tasks. |  | This could result in minor injuries, or in extreme case, be one of the causes of an accident with fatalities. Can result in loss of equipment or pollution release | Limit time spent in noisy environment Design of facilities to reduce stressful conditions / accommodations in quiet zones Regular breaks from routine tasks. Crew change and shift patterns to enable rest after travelling. |  | B3 | C3 | B3 | C3
No | PEOPLE | Not medically or physically fit | Failure to recognise unfit stakeholders can lead to injuries not only to themselves but others, The need replace or evacuate staffs unfit for tasks of their job description or to work offshore can have serious financial impact. Risk are normally accosted with Eyesight, Unfit body, Abnormal size, poor limb coordination |  | Loss of work due to illness/injury and replacement of staffs | Pre employment medical check UGUK Management of contractors/Clients to ensure recognised medical checks are in place |  | B2 | C3 | B1 | C3
No | PEOPLE | Reaction to medicine | In some cases, patients get allergic reactions to some drugs, changing a basic medical treatment into serious emergency. |  | Medical treatment will be needed, probably off site, can lead to LWDC and be potentially fatal Loss of production to evacuate | Medical records and history held on project by medic and/or Captain(confidential). Alternative medication held on project. Fully stocked hospital. 24 hour emergency line to doctor/hospital, Emergency response plan |  | B2 | C3 | B1 | C3
No | PEOPLE | Negative attitude toward HSE rule | In many cases, a known HSE rules is violated. This "I don't want" or "I cannot" attitude may be linked to various reasons and not necessarily linked to a sole individual. But a negative attitude toward HSE rule may trigger catastrophic accident scenario. |  | Injury's due to staffs taking short cuts or loss of asset | Training and induction of staffs to HSE Culture Implementation of consequence management Frequent site/workshop visits and walk rounds by management focusing on behaviour Implementation of BBS |  | B3 | B3 | B2 | B3
No | PEOPLE | Ergonomics (Human) | An incorrect posture or wrong position, can cause injury and be related to long term injury/illness, linked with manual handling. People working permanently in offices or workshops where they are desk bound due to bad seating position may also, on long term, induce back injuries. |  | Most common is lower back complaints | Office/workshop ergonomics issues identified, information passed to staffs Provide improved workstation ergonomics. Prevent hunching over laptop by supply 2nd adjustable screens Adjustable work surfaces. |  | B3 | B3 | B3 | C2
No | PEOPLE | Underestimation of risk and/or Overconfidence | The underestimation of risk poses the added risk of increased potential for loss. When persons do not understand the full characteristics of the risk before them, they are then led to make decisions based on their interpretations of the risk. Overconfidence is seen in many accident scenarios as a factor linked to the underestimation of risk due to routine tasks or young and inexperienced personnel (need to be proved) |  | Standdown required due to failure to manaage risk approperately resulting in financial loss Injurys can occur | Training and Mentoring / Implimentation of SSE program Review of TRA involvment in meetings Experienced supervision |  | B3 | C3 | B3 | C3
No | PEOPLE | Self medication and/or none disclosed medical condition | Staffs may have medincics that could result in an inability to function correctly, impairing safety of operations for personnel with sensitive positions. Obvious needs for the medicine is the treatment of medical conditions that may also result in a persons inability to function currently and put others at risk |  | Evacuation of employee due to none work lasted issue / financial Loss | Self medication should be eliminated as it impacts one's reactions and their ability to perform. Communication to Project Doctors and medical teams Disclosure in pre medical |  | B3 | C3 | B2 | C3
No | PEOPLE | Alcohol or drug abuse | Alcohol and drug abuse, by altering perception and behaviour may lead to highly hazardous situation , especially for personnel conducting critical activities (drivers, crane operators, pilots ...). |  | Injury's due to inattention caused by alcohol or drugs | Apply the SBGS Policy on Alcohol and drug abuse Intermittent tests for all stakeholders Consequence management applied |  | B3 | C3 | B1 | C3
No | PEOPLE | Life style choice | Some staffs choose life styles that can effect their work due to Ill health effects associated with their life style choice. Examples of the most common Smoking, non-healthy diet, Alcohol/drugs, lack of exercise These choices also at times have impact on others |  | Leading to time off work, due to Illness or injury (Heat attack most common) Has the potential to cut short a persons offshore working ability | Medical and Physical examinations (Fit to Work) Controlled diets on projects Posters and awareness on the ill health effects of smoking, drinking, poor diet and non exercise Supply exercise equipment Implement healthy life style / assist persons with their addictions |  | B3 | B3 | B3 | C3
No | PEOPLE | Panicking in emergency | Personnel can panic and lose control in a fire situation especially if seeing fire for the first time, or abandonment in difficult weather conditions, especially helicopter ditching. Personnel can panic and lose control of a serious injury situation. It may be the first time they have witnessed injury and pain. |  | Injury's ranging from FAC to LWDC (in extreme emergency's could be fatal) | Training and awareness Regular drills and exercises Ensure competency experience of key positions, (i.e. Masters, Pilots etc.…) |  | B3 | B4 | B3 | B4
No | PEOPLE | Trips / falls (ground level) | Any small ground obstacle may unbalance people walking through/past this obstacle, then sometimes falling on hazardous areas or sharp objects that they are carrying. On-board boats, vessels, continuous movement may easily unbalance the personnel, causing falls in exiguous and often hazardous places. |  | Minor injury's from FAC to MTC | Identification of trip hazards / markiong of trip hazards Handrails where steps are concerned for three points of contact. |  | B1 | B2 | B1 | C3
No | MANAGEMENT | PPE Selections and/or Maintenance | The associated risk with all individual tasks and operations is significantly enhanced if incorrect, defective or inadequate protective clothing and/or equipment is provided to accomplish the task. This will includes inadequate personal protective equipment (PPE) and maintenance of that equipment |  | Poor selection, improper use and inadequate maintenance of PPE can be an escalating factor increasing the likelihood of injury | PPE seletcion to a known standard Maintained as per manufactures instructions Personnel informaed and instructed on the use of PPE Consequence management applied for violation of PPE |  | B3 | C3 | B3 | C3
No | MANAGEMENT | Deficient machinery guard | All rotating machinery has to be considered as a serious risk of accident. Fingers, long hair, loose clothes may be caught by any rotating piece and generate a serious accident (contusion, lost of fingers ...). |  | Partial Permanent Disability, most common finger crushed | Ensure all guards are fit for purpose / working / inplace Part of inspection schedule Staffs informed of the risks of entrapment |  | B3 | C3 | B3 | C3
No | MANAGEMENT | Deficient maintenance | A good maintenance is the key to avoid problems on any kind of equipment. Preventive maintenance has to be considered as a real priority. A lack of maintenance or deficiency in maintenance may result in a failure of equipment when you must need it or when you are operating it. |  | As most of managerial factors in incident causation sequences, this hazard, associated to others, may indirectly lead to events with multiples fatalities and / or massive financial or reputation loss and / or catastrophic environmental consequences. | Reduction t maintenance by training / use of competent personnel, Engineering controls: design or procure equipment with regard to reduced maintenance requirements, Good spares levels maintained. Use of specialized third company maintenance personnel / services |  | B3 | C3 | C3 | C3
No | MANAGEMENT | Poorly designed equipment | The equipment (machinery, apparatus, gear, craft, vehicle ...) does not fulfil the function for which it was purchased. The equipment must be suitable to the work environment and then adequately designed for its use's purpose. A poorly design equipment may easily lead to major accidents. |  | Most likely outcome, financial loss due to removing non-functional equipment and paying replacment Injury can occur, severity pending type of equipment | Design equipment to known standards Involvment of HSE at design stage Testing equipment prior to mobilising |  | B3 | C3 | B3 | C2
No | MANAGEMENT | Deficient emergency / recovery planning | If the accident finally occurs, consequences may be very different depending on the level of preparation. A deficient emergency plan, disorganization may result in permanent disability or death. A non adapted recovery equipment or badly used may have the same consequences. |  | Failure leading to major loss In three key area, People/Financial/Environment | Inspection of HSE safety critical equipment Identification of required safety critical equipment/maintained and in working order to EU/OSHA/IMO requirements Ensure emergency plans are suitable for all foreseeable emergencys reviewed and tested regulary |  | B3 | C3 | C3 | C3
No | MANAGEMENT | Communication & Language deficiency's | Communications are a necessary operational requirement for both routine and emergency operations. A bad communication network affects immediately the quality of journey management and effectiveness of emergency responses; worse, a major accident may stay unworn several hours, delaying all recovery processes. Many different languages may be used on a crew. Misunderstanding of instructions, procedures, etc.. due to the difference of language between people may become the causes of accidents (lack of knowledge on how to operate). |  | Injury's due to poorly communicated information Loss of Asset/Production | Daily operational meetings. Defined organogram and communication hierarchy list. Provision of Scope of work and Project plan to Master and ROV PM (OVM). Language should be in English through all radio conversations. Use posters, signs and mix crews to enable common language. |  | B2 | B3 | A1 | C3
No | MANAGEMENT | Deficient Medical Equipment / Medicines and Qualified Staffing | Remote operations require a particular attention to the medical welfare afforded on projects, lack of medical equipment or medicine, can have serious consequences, additionally the staffing staffing needs to be such that can help and stabilise in remote locations. |  | Failure to stabilise IP or to impiment medical evacuation Impact financially due to evacuation of IP | Medical Supplier contract in place, covering staffing, equipment and medicines (full package) Medical supplier management Medicine under medical supplier MERP done by supplier and sufficient for remote risk. |  | B3 | C3 | B1 | C3
No | MANAGEMENT | Inadequate and/or insufficient selection of personnel | Inadequate personnel, i.e. badly trained, informed, unfit or insufficiently educated for a particular job may be the source of root causes of accident by lack of knowledge or competency. and can lead to extra work because of those inadequacies . Overload of work due to an insufficient number of personnel will increase by excess of tiredness, stress, risks of accident of any kinds |  | Can lead to stress and conflicts between staffs | Implementation of contractor management Selection of the right person for the tasks, i.e. through use of CV Ensure at project start skill levels and quantity's of staffs required are foreseen |  | B3 | C3 | B3 | C3
No | MANAGEMENT | Training deficiency Lack of Competency and/or certified personnel | Deficient personnel training prior to any kind of job may cause accidents by lack of knowledge on how to operate (vehicles, vessels, cranes, tools...), especially functions linked to critical activities. The bad use of the recovery equipment available (extinguisher, fire blanket, ...) may cause an extra accident in addition the bad use of safety equipment and PPE are effectively useless if crews do not know how to operate or wear them correctly .Many specialized tasks need personnel with specific competency, training and licensing and certified for that task, i.e. Master, Doctor |  | Finical impact of having to train contractors who should have the certification and/or replacement of staffs without certification | Training done at all levels, SBGS and project Follow up in SBGS on line training data base Identified key areas where certification is required, ensure certificate are followed at project level. Implementation of contractor management |  | B3 | C3 | B2 | C3
No | MANAGEMENT | Inadequate selection / management of subcontractor / Subcontractor Contracts | On a seismic crew, significant part of the activity is conducted by subcontractors (ship managers , chase vessels, ship yards , etc..). A poor process of evaluation, selection and follow up may jeopardize the safety of any operation managed by a subcontractor if they do not apply proper HSE standards and policies. If the terms of the contract between SBGS and its subcontractors do not clearly detail all requirements, the subcontractors may not identify gaps and then not bring a proper answer, creating a lack of resources and/or inadequate standards. |  | Lager fincail losses due to poor contractor management Injury's from FAC to Fatality Asset Loss Environment pollution | Major subcontractors (operating at risk activities such as ship managers, medical support suppliers,...) are evaluated and assessed against SBGS "contractor management" procedure. Good selection process managed onshore (SBGS Crewing and HR Manager): Recruitment of subcontracted personnel is based on assessment of their qualification, experience and trainings. Bridging interface document with subcontractors. Inductions given on site Information, training, instruction and supervision all given on site |  | B3 | C4 | B3 | C3
No | MANAGEMENT | Deficient information | A lack of communication to the project , especially information from the head office or the clients, may deprive the project of critical information to start. If the meetings are not properly planned, prepared and conducted, the needed HSE information is not given at the right time to the right persons. |  | Porject start delays is the most common issue with deficent information | Organisational structure understood by all stake holders Meeting schedules set Video conferances used as tool for remote assistance |  | B3 | B3 | B1 | B1
No | MANAGEMENT | Project Planning deficiency | Failure to follow proper planning methodology at tender and contract review stage and failing to implement the full scope of PEP (Project Execution Plan), at mobilization stage inadaquauate resources, standards and inappropriate methods being applied. |  | Loss of reputation with client Financial impact due to foreseen issues failing to be managed | Lead time for planning during bid stage, planning meetings, monitoring of planning stages, communication at all levels. PEP responsibility's defined, completed as scheduled as per contractual agreement. HAZID pre survey meeting / Pre Start up meetings ERP in place prior to mobilisation, tested after mobilisation. |  | C3 | C4 | B3 | B3
No | MANAGEMENT | Reporting deficiency | Failure of post accident reporting, including near misses, does not allow to conduct pertinent analysis and bring adequate corrective actions, promoting reoccurrence of accident scenarios. A poor reporting of positive activity does not allow implementation of preventative program to allow continuous improvement of the HSE management system. |  | Client complaints the most likley | Follow up of all events as per classification Impose management review, to ensure Top management involvement Follow strictly the SBGS event reporting process |  | B3 | B2 | B1 | B2
No | MANAGEMENT | Inspection / control deficiency | When activities and equipment are not properly inspected, non-conformities and unsafe conditions are not detected, offering preconditions to numerous accident scenarios. |  | Injury from FAC to PTD Asset Loss | Reduction of hazards by identification and implementation of Inspection routines. Inspection routines defined, Inspection and monitoring devices available and in good working order (sensors, pressure gauges etc.) |  | B3 | C3 | C3 | C3
No | MANAGEMENT | Deficient Event Investigation | When post incident investigations are not properly conducted, the quality of corrective actions do not prevent from reoccurrence. Sometimes, incidents with low consequences but potentially high consequences are not identified as such and then do not allow decisions and actions to be taken by competent parties. In addition, a lack of investigation after controls and inspections let unsafe conditions not being corrected by proper remedial actions. |  | Client complaints due to superficial investigation Failure to identify the root cause | Ensure a system of investigation follow up is implemented and agreed |  | C3 | B3 | B3 | B3
No | MANAGEMENT | Deficient Procedures / Work instruction and TRA's | A key aspect to assess hazards and conduct safely activities is to capture who is doing what and when in written procedures and work instructions: when they do not exist, are inaccurate or not communicated, learning are lost, new people not aware or practices are gradually changing, offering basement for catastrophic scenario. |  | Loss of productivity and/or asset due to poor safe work systems Can lead to injury's | Procedures written and approved at corporate level, in accordance with OMS operational policies Work instructions written and approved at project level (not overriding corporate procedure Regular review of TRA's by HOD / Creation of new TRA's by HOD |  | B3 | C3 | B3 | C3
No | MANAGEMENT | Insufficient travel / journey management | When journey management rules for air, water or land transport are not properly applied, the immediate detection of hazardous situations is affected. This can be staffs travel from home to project, or localised JM in country and around projects |  | Staffs lost on arrival in country, risks to the traveler not managed | Project TIS implemented for all travelling employees and delivered to contractor/clients. Phone contacts known Specific follow up of commercial staffs traveling to identified Risk Areas Transportation of staffs within country and/or project correctly monitored. |  | B2 | B2 | B2 | C3
No | MANAGEMENT | Inadequate definition of responsibilities | When HSE responsibilities are not clearly defined first in job descriptions and secondly in the execution of a project, and as of tender stage, we may expect some shortcomings in the planning and implementation. |  | Persons without authority effecting project/company matters | Bid and tender team set / responsibility's known Job description available on project inclusive of contractors and Clients on project. Responsibility's entered into all corporate procedures Organisational Charts, Corporate and at Project level, available and followed. |  | C3 | C4 | B1 | C2
No | MANAGEMENT | Inadequate definition of standard | Every time we design equipment, purchase equipment and goods, define work method and subcontract expertise ; if we do not integrate a clear reference to agreed HSE standards in our design specifications, purchasing data, quality processes, call for tender documents ; we may conduct operations with hazardous equipment, practices and/or breaking laws |  | Financial impact due to replacing non-standard products | Apply the SBGS known/agreed standards found in Guardian Measure standards against that of contractual agreement and/or Industry requirement Vessels to follow international standards (e.g. IMO /SOLAS / MARPOL etc. Identification of legal and legislation local requirements |  | B3 | C3 | A3 | B3
No | MANAGEMENT | Evaluation & risk management | Risk management is a main component of an efficient HSE system, taking place at all level of the organization, every time this risk assessment is not conducted or poorly realized, we expose our personnel and activities to non-recognized hazards, unplanned situations and / or inadequate controls and recoveries. |  | Financialand reputation loss due to not identifying foreseeable hazards that later cause downtime | HAZID Workshops pre mobilisation Project Risk assessments completed for foreseeable risks |  | C3 | B3 | B3 | C3
No | MANAGEMENT | Conflict of interest | Sometimes, production needs and HSE constraints are contradictory. To preserve presence on the market, when seismic companies are selected only on price criteria, operating standards are decreased as of tender stage. Some contract terms may generate conflict of interest, especially when heavy penalties are linked to mobilisation and/or downtime by clients, obliging crews to operate at the border of permitted operations. |  | Previous arrangements not available causing late start and penalty's applied | To negotiate penalty out of contact or decrease impact at bid stage and/or establish incentives by client. Contractor management |  | C4 | C4 | B1 | B3
No | MANAGEMENT | Audit & Review deficiency | If operations are not audited by their management or specialists, major deficiencies will not be identified. All HSE activity is measured with various indicators, pro-active or reactive, against predefined objectives and programs if management reviews are not or poorly organized to review the HSE performance, feedback will not be communicated, momentum will be lost |  | Reputation failing to meet contractual agreement | Implementation of auditing, Qualified/experienced auditors and selected observers. Use of standard auditing tools across company. Audits implemented from third parties. Actions and training to enable correct reviewing of audits, lessons learned from investigations (including identification of causal / root cause analysis). Document and procedure review, review of statistical information that may highlight deficiencies within organization |  | C3 | B3 | B1 | B1

## Risk Matrix
Likelihood
Severity |  | Reputation |  | Assets/ Financial | Environment | People |  | Improbable (A) | Unlikely (B) | Possible (C) | Likely (D) | Probable (E)
[8 empty] | Not known to have occurred in the Oil & Gas Industry | Has occurred in the Oil & Gas Industry | Has occurred in geophysical industry or similar Oil & Gas operations | Happens more than yearly in similar geophysical industry | Happens more than monthly in similar geophysical industry
| Negligible (1) | No Impact or Awareness |  | Up to $2,000 USD | Little or no potential for impact on the natural environment | First Aid Case |  | A1 | B1 | C1 | D1 | E1
| Minor (2) | Local Interest: Attention from local media and/or heightened concern by local community. Problems with local clients raised to on-site management |  | Up to $10,000 USD | Temporary impact on the natural environment - not violating law or regulation | Medical Treatment Case |  | A2 | B2 | C2 | D2 | E2
| Moderate (3) | Regional Interest: Attention from regional media and/or heightened concern by several local communities. Problems with regional clients raised to management level. NGO Attention |  | Up to $300,000 USD | Limited short term impact on the natural environment - without violation of law or regulation | Restricted or Lost Work Day Case in excess of 1 day but less than 100 days |  | A3 | B3 | C3 | D3 | E3
| Major (4) | National Impact: National concern and negative attention in the national media with potential for restrictive measures by local government. Significant adverse reaction from client organization |  | Up to $1,500,000 USD | Non-permanent or reversible impact on the natural environment that also violates law or regulation | Restricted or Lost Work Day Case in excess of 100 days |  | A4 | B4 | C4 | D4 | E4
| Catastrophic (5) | International Impact: Prolonged international media attention or widespread condemnation. Potential loss of multiple clients |  | Greater than $1,500,000 USD | Extended exposure with long term impact on the natural environment that also violates law or regulation | Loss of Life (Fatality) |  | A5 | B5 | C5 | D5 | E5
|  |  | Residual Risk Rating | Necessary Actions |  |  | Level of Authorization
|  |  | Green (Low) | Risk may be accepted without further action; However, the goal is to manage for continuous improvement to determine if risk can be reduced further. |  |  | Party Chief/Manager + On-Site QHSE Advisor
|  |  | Yellow (Medium) | Risk may be accepted under defined conditions of mitigation and prevention; Control to ALARP (As Low As Reasonably Practicable). |  |  | Project Manager + Operations Managers
|  |  | Red (High) | Risk is not acceptable; until more specific prevention/mitigation control measures are put in place to reduce to a lower residual risk rating.* |  |  | Business Line Operations Managers + SBGS Group Management

## Risk Lists
ENVIRONMENT | Threats from Invertebrate
Threats from Vertebrate
Infectious disease
Intestinal parasites
Contaminated food and water
Exposure to Air Pollutant (Natural Gas & H2s)
Extreme cold weather
Extreme heat weather
Cold water
High wind
Hurricane/Cyclone
Fog
Precipitations (rain, snow, hail)
Static electricity
Lightning
Rough sea
Tides
Slippery ground
Flotsam
Shallows
Visible obstacles
Hidden obstacles
Security / robbery (money, equipment)
Security / community
Security / civil unrest
Security / Piracy (terrorism)
EQUIPMENT | High noise / vibration generation
Deficient electrical systems
Engine and/or Power supply failure (Vessel)
Steering Failure (Vessel) Drifting
Hot surface and/or parts
High pressure system (Air/Hydraulic/Water)
Suspended equipment
Overhead obstacles / Falling equipment
Tense, rotating equipment
Erected object
Poor lighting
MATERIAL | Flammable and Combustible
Highly flammable
Carcinogenic, Mutagenic, Reprotoxic materials
Highly toxic
Toxic
Corrosive and harmful
Irritant
PROCESS | Road Transport / Traffic Event
Overloaded and/or Sudden movement of boat (SW vessels)
Man overboard
Colliding
Grounding
Helicopter Emergency (Ditching)
Incorrect use of ladders and scaffolding
Working aloft
Working at height
Manual handling
Working on active system
Working in confined spaces
Insufficient control of access
Housekeeping & Insufficient segregation of hazards
Lack of access to emergency equipment / lack of emergency exits
Crane and Hoisting Operations / Deficiency with attachment points
Diving Operations
Interacting with local culture
PEOPLE | Previous recurrent injury / disease
Fatigue / stress
Not medically or physically fit
Reaction to medicine
Negative attitude toward HSE rule
Ergonomics (Human)
Underestimation of risk and/or Overconfidence
Self medication and/or none disclosed medical condition
Alcohol or drug abuse
Life style choice
Panicking in emergency
Trips / falls (ground level)
MANAGEMENT | PPE Selections and/or Maintenance
Deficient machinery guard
Deficient maintenance
Poorly designed equipment
Deficient emergency / recovery planning
Communication & Language deficiency's
Deficient Medical Equipment / Medicines and Qualified Staffing
Inadequate and/or insufficient selection of personnel
Training deficiency/ Lack of Competency and/or certified personnel
Inadequate selection / management of subcontractor / Subcontractor Contracts
Deficient information
Project Planning deficiency
Reporting deficiency
Inspection / control deficiency
Deficient Event Investigation
Deficient Procedures / Work instruction and TRA's
Insufficient travel / journey management
Inadequate definition of responsibilities
Inadequate definition of standard
Evaluation & risk management
Conflict of interest
Audit & Review deficiency

## List (hidden)
A1 | A1
A2 | A2
A3 | A3
A4 | A4
A5 | B1
B1 | B2
B2 | B3
B3 | C1
B4 | C2
B5 | D1
C1 | E1
C2 | A5
C3 | B4
C4 | B5
C5 | C3
D1 | C4
D2 | D2
D3 | D3
D4 | E2
D5 | C5
E1 | D4
E2 | D5
E3 | E3
E4 | E4
E5 | E5